File-Share & On-Prem SharePoint → SharePoint Online Migration

Implementation Solution Guide

Version 1.0.0    ·    2026-07-07

# Contents

Right-click and choose “Update Field” to build the table of contents.

# Executive Summary — File-Share & On-Prem SharePoint → SharePoint Online Migration

Outcome. Legacy file servers and on-premises SharePoint content are moved into SharePoint Online cleanly — assessed and remediated, mapped to a governed target information architecture, migrated with permissions intact, and validated with evidence — so content lands organized and governed, not as a cloud copy of the old mess. The result is retired file servers and on-prem farms, lower infrastructure cost and risk, and content that people can actually find and that the business can actually govern.

The problem it solves. The tempting shortcut — drag everything up with a copy tool — recreates every legacy problem in a platform where they cost more and are harder to fix: broken permissions, folders nested past the platform's limits, filenames SharePoint rejects, oversized files that fail mid-copy, and no owner for anything. Migrations that skip assessment discover these failures at scale, on cutover night, and slip by weeks.

The approach. A repeatable, pilot-first method using only supported Microsoft tooling (Migration Manager and the SharePoint Migration Tool / SPMT) and PowerShell:

Assess the source for the blockers that fail SPO migrations (path/URL length, invalid

characters, blocked types, oversized files, permission surface).

Design a governed target IA and a permission map (source principals → SPO/M365/Entra groups),

resolving every principal rather than guessing.

Configure the migration tool from the map (bulk tasks, migrate-permissions settings).

Pilot one representative scope end-to-end using pre-stage + delta — the bulk copy runs

while users keep working, and only the changes move during a short read-only cutover window.

Validate with counts, a permission spot-check, and a delta-clean check — an explicit pass/fail

gate — then Expand wave by wave, retiring each source only after its gate passes.

Why it's low-risk. The source stays authoritative and read-only — never destroyed — until each wave's validation gate passes, so rollback is simply lifting the freeze and redirecting users back. Assessment, permission-mapping, and validation are read-only; the only data-moving step is gated behind an explicit -Commit. Pre-stage + delta shrinks the downtime window from days to hours. Compliance and legal determinations (retention, legal hold, records schedules) remain with the organization's compliance function — this solution provides the technical method and the evidence, not the determination.

What's included. Solution overview, requirements guide, step-by-step implementation, testing/ validation procedures, troubleshooting, best practices, and five PowerShell tools — source assessment, permission mapping, task builder + runner (safe-by-default), post-migration validation, and a scope/health helper — all read-only or dry-run by default, with no credentials in code.

Bottom line. Legacy content moved to SharePoint Online the right way — assessed and remediated, mapped to a governed target IA, migrated with permissions and validated — organized, not a cloud repeat of the mess.

# 1. Solution Overview — File-Share & On-Prem SharePoint → SharePoint Online Migration

## What this solution is

Legacy file servers and on-premises SharePoint Server farms are expensive to run, hard to secure, and increasingly a liability — but the naive fix (copy everything up with a drag-and-drop tool) simply recreates the mess in the cloud: broken permissions, orphaned folders nested twenty levels deep, filenames the platform rejects, and no owner for anything. This solution is a repeatable, pilot-first method to migrate file shares and on-prem SharePoint content into SharePoint Online (SPO) and OneDrive cleanly — assess and remediate the source, map it to a governed target information architecture (IA), execute with Microsoft's supported migration tooling (Migration Manager and the SharePoint Migration Tool / SPMT) using a pre-stage + delta pattern, map permissions, and validate that content and access actually landed.

It uses only supported Microsoft tooling and PowerShell (SharePoint Online Management Shell, PnP PowerShell, the SPMT PowerShell module, and Microsoft Graph). The migration-tool *console internals* (the Migration Manager agent UI, the SPMT desktop wizard screens) are deferred to Microsoft's product documentation — this solution gives you the procedure, sequencing, and automation around them, which is where migrations actually succeed or fail.

Scope boundary. This is an on-prem / file-share → SharePoint Online migration. It is distinct from any SPO → other-platform migration (e.g. SPO → Google Drive), which moves in the opposite direction with different tooling. Source here = Windows/NAS file shares (SMB/UNC) and on-premises SharePoint Server (2013/2016/2019/Subscription Edition) document libraries. Target = SharePoint Online team/communication sites and OneDrive for Business.

## Why this matters

A bad migration is worse than no migration. Lift-and-shift with no remediation carries every

legacy problem — nested-permission sprawl, dead content, unresolvable names — into a platform where   they are harder to fix and now cost you per-GB.

The platform will silently reject content you didn't remediate. Path/URL length over the SPO

limit, blocked file types, invalid characters, and oversized files fail *during* the migration —   discovering that on cutover night, at scale, is how migrations slip weeks.

Permissions are the hardest part and the part tools do worst. NTFS ACLs and on-prem SharePoint

groups do not map one-to-one to SPO/M365 groups. Getting this wrong either over-shares (a   compliance incident) or locks people out (a flood of tickets) on day one.

Without a target IA, you pave the cow paths. Deciding *where* content lands — which site, which

library, which hub — before you move it is what turns a migration into a cleanup.

Delta migration is what makes cutover safe. Pre-staging the bulk while the source stays live,

then moving only the changes at cutover, shrinks the freeze window from days to hours.

## How it works

Assess the source. Scan file shares (and inventory on-prem SharePoint libraries) for the things

that break SPO migrations: path/URL length approaching the limit, invalid characters and    reserved names, blocked file types, oversized files, very large libraries/folders, and the    permission model (NTFS ACLs, share permissions, on-prem SP groups). The output is a factual    inventory and a remediation punch-list.

Remediate the source (or plan around it). Fix or flag each blocker: shorten paths, rename

invalid items, remove or archive blocked/dead content, split oversized structures. Remediation is    staged and reversible; nothing is changed in production without a report and an approval.

Design the target IA. Map each source share/library to a target site → library → folder

and to a hub, applying a naming convention and a governance model (owners, sharing, retention    intent — with the compliance *determination* deferred to the records/legal function). This is a    *mapping*, not a copy of the source tree.

Map permissions. Translate each source principal (NTFS group, on-prem SP group, individual

ACE) to a target SPO group / M365 group / Entra security group and a permission level. Where a    clean mapping doesn't exist, it is flagged for a decision rather than guessed.

Configure the migration tool. Choose Migration Manager (agent-based, best for many file

shares and on-prem SP at scale, tasks defined in the SharePoint admin center) or SPMT (desktop    / PowerShell, best for smaller or scripted runs); register the target, define tasks from the    mapping (bulk CSV/JSON), and set the settings (permissions, versions, filters).

Pre-stage, then delta. Run a full pre-stage pass while the source stays read/write, then —

at the agreed cutover window — set the source read-only and run an incremental (delta) pass    that moves only what changed. This is the pattern both Microsoft tools support for a low-downtime    cutover.

Validate. Compare source vs. target item counts, spot-check permissions, confirm

metadata/versions per the settings chosen, and confirm the delta is clean (nothing left behind).    Only then is the source decommissioned per the org's retention rules.

## Reference design (what "good" looks like)

A pilot wave (one representative share or on-prem site collection) proves the whole

assess → remediate → map → migrate → validate chain end-to-end before any broad wave.

Bulk migration runs from a migration workstation/agent with line-of-sight to the source (SMB /

on-prem SP) and to SPO, using Migration Manager agents (scaled out for throughput) or SPMT.

Content lands in a governed target IA — communication/team sites under hubs, with owners,

sharing settings, and retention intent applied — not a mirror of the old drive letters.

Every wave uses pre-stage + delta so the business keeps working on the source until a short,

scheduled cutover.

A validation gate (counts + permissions + delta-clean) must pass before a wave is called done

and the source is retired.

## Naming convention (used in every doc and script)

Every artifact this solution creates is named <Purpose> – <Scope> – <Stage> and reused verbatim across the docs, scripts, the SharePoint admin center, and the migration tool. The standard set:

| Artifact | Name |
| --- | --- |
| Source assessment export | Source Assessment – FileShare+SP – Discovery |
| Remediation punch-list | Remediation Plan – Source – PreMigration |
| Target IA / destination map | Target IA Map – SPO – Design |
| Permission mapping table | Permission Map – Source→SPO – Design |
| Pilot migration task | Migration Task – Pilot – Wave0 |
| First broad wave task | Migration Task – Finance – Wave1 |
| Cutover runbook (per wave) | Cutover Plan – <Scope> – <WaveN> |
| Post-migration validation report | Post-Migration Validation – <Scope> – Validate |
| Target site (pilot) | SPO Site – Pilot – Prod |

## Benefits

Content lands organized and governed, not a cloud copy of the legacy mess.

No cutover-night surprises — blockers are found and fixed in assessment, not discovered at scale.

Permissions arrive intact and intentional, mapped to modern SPO/M365 groups.

Low-downtime cutover via pre-stage + delta.

Evidence of success — counts and permission validation prove the migration, per wave.

## Limitations (be honest with buyers)

Migration-tool console internals are deferred to Microsoft docs. This solution gives the method,

sequencing, task definitions, and PowerShell — not a screen-by-screen tour of the Migration Manager   or SPMT UI, which Microsoft documents and changes.

SPO service limits are Microsoft's, not ours, and change. Path/URL length, file-size, blocked

file types, and list-view limits are enforced by the service; the exact current values must be   verified against Microsoft's documentation for your tenant/cloud (see Requirements/Testing).

Government and sovereign clouds differ. GCC High / DoD (*.sharepoint.us / *.office365.us)

and other sovereign clouds can differ in tool support, endpoints, and limits — verify in your   tenant; do not assume Commercial behavior.

Not every source is tool-supported. Encrypted, in-use, or exotic sources (e.g. some NAS

permission models, IRM/RMS-protected files, third-party ECM) may need vendor tooling or manual   handling; those are integrated at the pattern level and deferred to the vendor's docs.

Compliance/legal determinations are out of scope. What to retain, what is under legal hold, and

which records schedule applies are decided by the org's compliance/records/legal functions —   this solution provides the technical method and evidence, not the determination.

## The standard deployment model

Assess and remediate the source → design the target IA and permission map → configure the tool → run a pilot wave (pre-stage + delta) and validate → expand wave by wave, retiring each source only after its validation gate passes. Pattern: Assess → Design → Configure → Pilot → Validate → Expand, with explicit pass/fail gates and a documented rollback (the source stays authoritative until validation passes).

# 2. Requirements — File-Share & On-Prem SharePoint → SharePoint Online Migration

These are the solution-specific prerequisites for migrating file shares and on-premises SharePoint Server content into SharePoint Online. They build on top of the shared global-requirements-sharepoint.md (M365 tenant with SPO/OneDrive and licensing; least-privilege SharePoint Administrator access; SPO Management Shell / PnP / Graph toolchain; a defined information architecture and identity/group source of truth; a pilot scope and change control; and security / compliance / records stakeholder engagement). Verify the six shared requirements first, then the migration-specific items below. Each item: Description / Why / Verify / Implement if missing.

__________________________________________________

## 1. Source access — file shares and/or on-prem SharePoint

Description: Read access to the migration sources: file shares by UNC path (SMB) with an

account that can read the files and their NTFS ACLs, and/or on-premises SharePoint Server   (2013/2016/2019/Subscription Edition) with a farm/site-collection account that can read the content   databases/libraries the migration tool will pull from.

Why required: Assessment, remediation, permission mapping, and the migration tool all read

directly from the source; without ACL-read rights the permission map is incomplete.

How to verify: From the migration workstation, Get-ChildItem \\server\share -Recurse and

Get-Acl succeed; for on-prem SP, confirm the tool's supported version and that the account can   enumerate the target webs/libraries.

How to implement if missing: Grant a dedicated migration service account read (and ACL-read)

on the shares and the required least-privilege role on the SharePoint farm; confirm the on-prem SP   version is supported by the chosen tool (verify in Microsoft's Migration Manager / SPMT docs).

## 2. A migration workstation / agent with line-of-sight to source and SPO

Description: A domain-joined Windows machine (or set of machines) that can reach the source over

SMB / the on-prem SP endpoint and reach SharePoint Online over HTTPS (443), meeting the chosen   tool's requirements — for Migration Manager, the migration agent installed and registered;   for SPMT, the SharePoint Migration Tool and/or its Microsoft.SharePoint.MigrationTool.PowerShell   module.

Why required: The tool moves bytes through this host; throughput, reliability, and the delta

passes all depend on it. Multiple agents scale throughput for large estates.

How to verify: The agent shows online/healthy in the SharePoint admin center (Migration

Manager), or Import-Module Microsoft.SharePoint.MigrationTool.PowerShell loads and   Register-SPMTMigration connects (SPMT).

How to implement if missing: Provision the host(s), install the agent/SPMT per Microsoft's

current install docs, and allow outbound 443 to the SPO/Microsoft 365 endpoints (verify the current   endpoint list for your cloud).

## 3. Migration tooling chosen and its version confirmed

Description: A decision on the migration engine — Migration Manager (agent-based, tasks

defined in the SharePoint admin center, strong for many file shares and on-prem SP at scale),   SPMT (desktop/PowerShell, strong for smaller or scripted runs), or an approved third-party   tool — with its current version installed.

Why required: Task definition, CSV/bulk format, supported sources, and the pre-stage/delta

behavior differ per tool; the provided SPOMIG-TaskBuilder.ps1 targets the SPMT PowerShell   module and emits a Migration Manager–compatible bulk CSV.

How to verify: The tool launches, signs in to your tenant, and lists its supported source types

and limits (confirm against Microsoft's docs).

How to implement if missing: Install the current tool; if using a third-party engine, its

console is deferred to the vendor's docs — this solution still supplies the assessment, mapping,   and validation around it.

## 4. Target SharePoint Online IA provisioned (or ready to provision)

Description: The target sites, libraries, and hubs that content will land in — named per the

Target IA Map – SPO – Design — provisioned or scripted for provisioning, with the intended   owners and sharing posture set.

Why required: Migration tasks need a destination URL; migrating into an ungoverned or

not-yet-created site is how content lands orphaned.

How to verify: The target site URLs resolve and the migration account can write to them

(Connect-PnPOnline + Get-PnPWeb succeed on the destination).

How to implement if missing: Provision the target IA first (often the *SharePoint Online

Architecture & Site Provisioning* solution); at minimum create the pilot target SPO Site – Pilot –   Prod before the pilot wave.

## 5. Sufficient SharePoint Online storage and a checked list of service limits

Description: Enough tenant + per-site storage for the migrated content, and a documented

check of the current SPO migration-relevant service limits: URL/path length, file-size limit,   invalid characters / reserved names, blocked file types, and per-library/list-view thresholds.

Why required: Insufficient storage stalls a wave; unremediated limit violations fail items

mid-migration. These limits are Microsoft's and can change — they must be read from current docs   or measured, not assumed.

How to verify: In the SharePoint admin center check tenant/site storage; confirm the current

limit values in Microsoft's SharePoint limits documentation for your cloud (Commercial vs   Government may differ).

How to implement if missing: Increase storage / adjust quotas; feed the confirmed limit values

into the assessment (SPOMIG-Assessment.ps1 accepts them as parameters so the check tracks the   real, current numbers).

## 6. Identity mapping — source principals resolve to Entra ID / M365 groups

Description: A way to resolve source principals (NTFS local/domain groups, on-prem SP groups,

individual users) to Entra ID users/groups, so permissions can be mapped to SPO groups / M365   groups / Entra security groups in the target.

Why required: Permission mapping is only possible if source identities correspond to cloud

identities; unmatched principals must be surfaced for a decision, not dropped.

How to verify: Users/groups from the source ACLs exist in Entra ID (spot-check with Graph or

Get-PnPAzureADGroup / Get-MgUser); confirm whether Entra Connect hybrid sync is in place.

How to implement if missing: Ensure directory sync / identity provisioning is complete for the

in-scope population before the permission map is finalized; SPOMIG-PermissionMap.ps1 reports   unmatched principals so gaps are explicit.

## 7. A cutover window and change control for each wave

Description: An agreed cutover window per wave during which the source can be set

read-only, the delta pass runs, and users are redirected — under the change-control process from   the shared requirements.

Why required: The pre-stage/delta pattern needs a defined moment to freeze the source; migration

cutover is high-impact (users switch to a new location) and needs approval and a rollback.

How to verify: A named change window, an approver, a user-communication plan, and a rollback

(source stays authoritative until validation passes) are documented in the Cutover Plan for the   wave.

How to implement if missing: Schedule the window, draft the comms, and document the rollback

before the wave's delta/cutover step.

__________________________________________________

*All six shared SharePoint requirements plus these seven migration-specific items should be green before the pilot wave. The migration follows the house model — Assess → Design → Configure → Pilot → Validate → Expand — with the source remaining authoritative until each wave's validation gate passes. Automation is PowerShell with no hardcoded credentials or secrets.*

# Global Requirements — SharePoint Online & OneDrive Solutions

These requirements apply to every solution in the SharePoint category (SharePoint Online architecture & provisioning, external sharing, OneDrive for Business, migration to SPO, permissions, search, and records/retention). Verify each before starting a solution's implementation steps.

Vendor boundary (applies to every SharePoint solution). The SharePoint admin center, the Microsoft 365 admin center, the SharePoint Online Management Shell and PnP PowerShell, and Microsoft Graph are authored at exact, current click-by-click / cmdlet detail from Microsoft's public documentation. Where a capability, setting, or portal path is plan- or version-dependent (storage limits, sharing controls, Syntex/records features, Commercial vs Government cloud), it is cited or flagged "verify in your tenant" — never invented. Third-party migration and governance tools (e.g. ShareGate, Migration Manager, AvePoint) are integrated at the pattern level; their consoles are deferred to the vendor's docs. Automation is PowerShell (SPO Management Shell / PnP / Graph) — never with hardcoded credentials or secrets.

## 1. Microsoft 365 tenant with SharePoint Online / OneDrive and licensing

Description: A Microsoft 365 tenant with SharePoint Online and OneDrive for Business and

the licensing the capability requires (e.g. an E-plan for advanced records/retention, Syntex where used).

Why required: All site, sharing, OneDrive, and records configuration depends on the right plan.

How to verify: In the M365 admin center confirm the SharePoint/OneDrive subscription and add-ons.

How to implement if missing: Assign/purchase the required licensing before starting.

## 2. Administrative access (least-privilege SharePoint roles)

Description: Access with the least-privilege role the solution names — typically **SharePoint

Administrator** (and Global Administrator only where genuinely required, e.g. tenant-wide sharing).

Why required: Tenant/site settings, sharing, provisioning, and records changes require the role.

How to verify: Confirm the role in the M365 admin center / Entra roles.

How to implement if missing: Have a Global Admin assign the least-privilege role under change control.

## 3. SharePoint Online Management Shell / PnP + Graph toolchain

Description: A workstation with the SharePoint Online Management Shell and/or **PnP

PowerShell** (and Graph PowerShell where used), modern-auth / MFA-capable admin sign-in (PnP app   registration where required).

Why required: Configuration, automation, and the provided scripts run through SPO/PnP/Graph.

How to verify: Connect-SPOService / Connect-PnPOnline succeeds; modules installed.

How to implement if missing: Install the modules; register the PnP app where needed; confirm sign-in.

## 4. Information architecture & identity/group source of truth

Description: A defined information-architecture intent (hub/site structure, taxonomy) and the

identity/group source (Entra ID groups, M365 Groups backing team sites) that drives access.

Why required: Provisioning, permissions, search, and governance key off the IA and groups.

How to verify: Confirm the intended hub/site structure and which groups model is authoritative.

How to implement if missing: Define the IA and group model (often the Architecture solution) first.

## 5. A pilot scope and change control

Description: A pilot site collection / hub / user set to validate on before tenant-wide

rollout, and a change-control process for production changes (sharing, permissions, retention,   migration cutover are high-impact).

Why required: Every solution follows an Assess → Design → Configure → Pilot → Validate → Expand

model; tenant-wide sharing/permission/retention changes are high-impact.

How to verify: Confirm a named pilot scope and an approval/change window are available.

How to implement if missing: Create a pilot scope and agree change control before production changes.

## 6. Security, compliance & records stakeholders

Description: Engagement with the security, compliance/records, and data-governance stakeholders

whose policies the configuration must satisfy (external sharing, permissions, retention/records,   sensitivity).

Why required: Sharing, permission, and records settings must align to enterprise policy.

How to verify: Confirm the applicable policies and named approvers.

How to implement if missing: Identify the owners and capture requirements before configuring governance.

*The deployment model across every SharePoint solution is the same: Assess → Design → Configure → Pilot → Validate → Expand, with explicit pass/fail gates and a documented rollback for production changes. Automation is delivered as PowerShell (SPO Management Shell / PnP / Graph) — never with hardcoded credentials or secrets in code.*

# 3. Implementation — File-Share & On-Prem SharePoint → SharePoint Online Migration

Follow these steps in order. The migration is structured Assess → Design → Configure → Pilot → Validate → Expand. Every artifact is named <Purpose> – <Scope> – <Stage> and reused verbatim in later steps, testing, troubleshooting, and the scripts. The source stays authoritative until each wave's validation gate passes — that is the rollback.

Safety posture. Assessment and validation are read-only. The remediation and the migration execution change data — those steps default to report / dry-run and require an explicit -Commit (or the equivalent approval) before anything is written or moved. Never run a broad wave before the pilot's validation gate passes.

__________________________________________________

## Phase A — Assess the source

### A1. Inventory the migration sources

List every in-scope file share (by UNC path) and every in-scope on-prem SharePoint site

collection / library. Record the owner and rough size of each.

Confirm source read + ACL-read access from the migration workstation (Requirements §1).

### A2. Run the source assessment (read-only)

Run SPOMIG-Assessment.ps1 against each source, passing the current SPO limits you

confirmed (Requirements §5) so the check tracks Microsoft's real numbers:

.\SPOMIG-Assessment.ps1 -Path \\fs01\Finance -MaxUrlLength 400 -MaxFileSizeGB 250 -CsvPath .\SourceAssessment.csv

The script flags, per item: path/URL length near the limit, **invalid characters / reserved

names, blocked file types, oversized files, deep nesting, and it summarizes the    permission surface** (distinct principals in the ACLs).

Save the export as Source Assessment – FileShare+SP – Discovery.

Gate A (assessment complete): every source has an assessment export and a blocker count. Do not

design the target until the true blocker picture is known.

__________________________________________________

## Phase B — Design the target and the remediation

### B1. Build the remediation punch-list

From Source Assessment – FileShare+SP – Discovery, list each blocker with its fix: shorten path,

rename invalid item, remove/archive blocked or dead content, split an oversized folder/library.

Record it as Remediation Plan – Source – PreMigration, noting which fixes happen at source

(rename before migrating) vs. in-flight (the tool can rename on ingest — confirm the tool's    behavior in its docs).

Compliance note: whether legacy content is *retained, archived, or deleted* is a

compliance/records/legal determination — this plan records the technical action, not the    decision to keep or destroy.

### B2. Design the target IA and destination map

Map each source share/library to a target site → library → folder and a hub, applying the

naming convention and the intended owners and sharing posture. Do not mirror drive letters or    deep legacy trees — flatten and organize.

Record it as Target IA Map – SPO – Design (source path → destination URL, one row per task).

This map is the input to the migration task builder.

Provision (or confirm) the target sites, including at minimum the pilot target **`SPO Site – Pilot –

Prod`**.

### B3. Build the permission map

Run SPOMIG-PermissionMap.ps1 (read-only) to enumerate source principals and propose a target

mapping (NTFS/SP group → SPO group / M365 group / Entra security group + permission level):

.\SPOMIG-PermissionMap.ps1 -Path \\fs01\Finance -CsvPath .\PermissionMap.csv

Review every row; resolve unmatched principals (the script flags them) with a decision, not a

guess. Prefer mapping to groups, not individuals.

Save as Permission Map – Source→SPO – Design.

Gate B (design complete): remediation plan approved, target IA map complete, permission map has

zero unresolved principals.

__________________________________________________

## Phase C — Configure the migration tool

### C1. Verify tenant + target readiness (read-only)

Run SPOMIG-ScopeHealth.ps1 to confirm the target site exists and is writable, storage is

sufficient, and the migration prerequisites are green:

.\SPOMIG-ScopeHealth.ps1 -SiteUrl https://contoso.sharepoint.com/sites/PilotProd

Resolve anything red before defining tasks.

### C2. Register the tool and define tasks from the map

Migration Manager path: in the SharePoint admin center → Migration, confirm the agent is

online/healthy, then create a bulk migration and upload the CSV emitted from the map (see    C3). *The Migration Manager console UI is deferred to Microsoft's docs.*

SPMT / PowerShell path: run SPOMIG-TaskBuilder.ps1 to turn Target IA Map – SPO – Design

into migration tasks. By default it builds the bulk CSV and does a dry-run — it only registers    and starts a migration when you pass -Commit:

.\SPOMIG-TaskBuilder.ps1 -MapCsv .\TargetIAMap.csv -BulkCsvOut .\SPMT-Bulk.csv    # dry-run: build + validate CSV

Set the migration settings to match the design: migrate permissions (per the permission

map), version history depth, filters (skip blocked/dead content), and whether the tool renames    invalid items in-flight (confirm the exact settings names/behavior in the tool's current docs).

### C3. Name the tasks

Name the pilot task Migration Task – Pilot – Wave0 and each subsequent wave

Migration Task – <Scope> – Wave<N> (e.g. Migration Task – Finance – Wave1). Reuse these    names in the tool, the validation, and the cutover plan.

__________________________________________________

## Phase D — Pilot wave (pre-stage → delta → validate)

### D1. Pre-stage the pilot (source stays live)

With the source still read/write, run the pilot pre-stage pass — the full copy — for

Migration Task – Pilot – Wave0:

SPMT/PowerShell: .\SPOMIG-TaskBuilder.ps1 -MapCsv .\TargetIAMap-Pilot.csv -BulkCsvOut .\SPMT-Pilot.csv -Commit

Migration Manager: start the pilot task from the admin center.

Let it complete; review the tool's per-item result report for failures and re-run/repair as needed.

Users keep working on the source — nothing has cut over yet.

### D2. Cutover: freeze, delta, redirect

In the agreed window (Cutover Plan – Pilot – Wave0): set the pilot source read-only (remove

write on the share / set the on-prem library read-only), announce the freeze.

Run the incremental (delta) pass — it moves only what changed since pre-stage (both tools

support incremental re-runs of the same task).

Redirect users to the target SPO Site – Pilot – Prod (updated shortcuts / links / comms).

### D3. Validate the pilot (read-only) — the gate

Run SPOMIG-Validation.ps1 to compare source vs. target and spot-check permissions:

.\SPOMIG-Validation.ps1 -SourcePath \\fs01\PilotFinance -SiteUrl https://contoso.sharepoint.com/sites/PilotProd -Library "Documents" -CsvPath .\PilotValidation.csv

Save as Post-Migration Validation – Pilot – Validate.

Gate D (pilot pass/fail):

PASS if: target item count ≥ source (net of intentionally filtered content), **permission

spot-check matches the permission map, versions/metadata match the chosen settings, and the      delta report shows nothing left behind**.

FAIL if any of the above is off → roll back (source is still authoritative and read-only

can be lifted), fix the mapping/settings/remediation, and re-run. Do not expand on a failed pilot.

__________________________________________________

## Phase E — Expand wave by wave

### E1. Repeat the proven chain per wave

For each subsequent scope (e.g. Migration Task – Finance – Wave1), reuse the exact pattern:

assess → remediate → confirm map → pre-stage (source live) → delta cutover (source read-only) →    validate.

Save each wave's evidence as Post-Migration Validation – <Scope> – Wave<N> and pass its gate

before retiring that source.

### E2. Retire the source (only after the gate)

After a wave's validation passes and a defined soak period elapses, decommission the source per

the org's retention rules — the *decision* to delete or archive is the compliance/records    function's, executed here as the technical step.

Update the migration tracker: waves complete, sources retired, validation evidence filed.

__________________________________________________

## Rollback (every wave)

Because pre-stage runs while the source is live and the source is only ever set read-only at cutover (never deleted at cutover), rollback is: lift read-only on the source, redirect users back, and re-plan. The source remains the authoritative copy until that wave's validation gate passes and the soak period ends. No source is destroyed on the strength of an unvalidated migration.

# 5. Testing & Validation — File-Share & On-Prem SharePoint → SharePoint Online Migration

Each test states how to run it and the expected pass/fail signal. Assessment and validation are read-only. Run the pilot-scope tests before any broad wave; re-run the per-wave tests for every subsequent wave. The overall gate is: content migrated (counts), permissions migrated (spot-check), delta clean, target governed.

__________________________________________________

## Test 1 — Assessment completeness (pre-migration)

Run: .\SPOMIG-Assessment.ps1 -Path \\fs01\PilotFinance -MaxUrlLength <current-limit> -MaxFileSizeGB <current-limit> -CsvPath .\a.csv

PASS: The export Source Assessment – FileShare+SP – Discovery exists and reports a blocker

count for path length, invalid characters, blocked types, and oversized files, plus a distinct-   principal count for the permission surface.

FAIL: The scan errors, misses subtrees (access denied), or the limit parameters don't match the

current Microsoft-documented values → fix access / confirm current limits and re-run.

## Test 2 — Remediation punch-list resolves every blocker

Run: Reconcile Remediation Plan – Source – PreMigration against the assessment export.

PASS: Every blocker in the assessment has a corresponding fix (at-source rename/shorten/remove,

or an in-flight tool rename confirmed against the tool's docs). Zero blockers are unaddressed.

FAIL: Any assessed blocker has no planned fix → resolve before configuring tasks (unremediated

blockers fail mid-migration).

## Test 3 — Permission map has no unresolved principals

Run: .\SPOMIG-PermissionMap.ps1 -Path \\fs01\PilotFinance -CsvPath .\pm.csv then review the

Unmatched column.

PASS: Permission Map – Source→SPO – Design maps every source principal to an SPO/M365/Entra

target with a permission level; zero rows flagged unmatched; mappings favor groups over   individuals.

FAIL: Any principal is unmatched or maps to an individual where a group exists → resolve with a

decision before migrating (prevents day-one over-share or lockout).

## Test 4 — Target readiness (scope/health)

Run: .\SPOMIG-ScopeHealth.ps1 -SiteUrl https://contoso.sharepoint.com/sites/PilotProd

PASS: Target site resolves and is writable by the migration account, storage is sufficient for

the wave, and the reported prerequisites are green.

FAIL: Site missing/not writable, storage short, or a prerequisite red → resolve before defining

tasks.

## Test 5 — Task build validates (dry-run)

Run: .\SPOMIG-TaskBuilder.ps1 -MapCsv .\TargetIAMap-Pilot.csv -BulkCsvOut .\SPMT-Pilot.csv

(no -Commit).

PASS: A well-formed bulk CSV is produced, every row has a valid source and a resolvable

destination URL, and the dry-run reports no structural errors. No migration is started (safe   default).

FAIL: Malformed rows, unresolved destinations, or the script attempts to move data without

-Commit → fix the map / do not proceed.

## Test 6 — Pre-stage pass completes

Run: Execute the pilot pre-stage (-Commit / start the Migration Manager task) with the source

read/write.

PASS: The tool's per-item report shows all in-scope items migrated (or only expected filtered

skips); failures are re-run/repaired to zero. Users are still working on the live source.

FAIL: Persistent per-item failures → map to a root cause (see Troubleshooting) and repair before

cutover.

## Test 7 — Delta cutover is incremental and clean

Run: Set the source read-only, run the incremental (delta) pass for the same task.

PASS: The delta pass moves only changed items (not a full re-copy) and completes with

nothing left behind; the tool reports the incremental set.

FAIL: The pass re-copies everything (task identity changed) or reports items it could not carry

→ confirm the same task/mapping is reused and repair.

## Test 8 — Item-count reconciliation (source vs target)

Run: .\SPOMIG-Validation.ps1 -SourcePath \\fs01\PilotFinance -SiteUrl <site> -Library "Documents" -CsvPath .\v.csv

PASS: Target item count ≥ source count net of intentionally filtered content; the report

Post-Migration Validation – Pilot – Validate shows the reconciliation.

FAIL: Target short of source beyond the known filter set → investigate the missing items before

passing the gate.

## Test 9 — Permission spot-check matches the map

Run: Use the validation report's permission section (and spot-check in the SPO UI) against

Permission Map – Source→SPO – Design for a sample of libraries/folders.

PASS: Sampled target permissions match the mapped groups and levels — no unexpected broad access,

no missing access for a mapped group.

FAIL: Over-share (e.g. "Everyone"/broad group where the map said a scoped group) or a mapped

group missing → remediate permissions before declaring the wave done.

## Test 10 — Target governance applied

Run: Confirm the target site/library has the intended owner, sharing posture, and any

retention intent label from the design (compliance *determination* deferred to records/legal).

PASS: Owner set, sharing matches design, retention intent applied where required.

FAIL: Orphaned site (no owner), sharing looser than design, or missing retention intent →

apply before retiring the source.

__________________________________________________

### The wave gate (all must pass to expand / retire the source)

Test 8 — counts reconcile.

Test 9 — permissions match the map.

Test 7 — delta clean, nothing left behind.

Test 10 — target governed.

If any fail, roll back (source is still authoritative; lift read-only) and re-run. Do not expand on a failed pilot, and do not retire a source until its wave gate passes and the soak period ends.

# 6. Troubleshooting — File-Share & On-Prem SharePoint → SharePoint Online Migration

Common failure modes and how to resolve them. Symptoms are grouped by phase. Where a limit or behavior is Microsoft's and version/cloud-dependent, verify the current value in Microsoft's docs for your tenant/cloud rather than assuming.

__________________________________________________

## Assessment & remediation

### Items fail migration for "path too long" even though the source path looked fine

Cause: The failure is the projected SPO URL length (target site URL + relative path, with

spaces URL-encoded), not the raw source path — the destination base adds length.

Resolve: Re-run SPOMIG-Assessment.ps1 with the real target base URL (-TargetBaseUrl) and

the current -MaxUrlLength; shorten deep folders or land the content under a shorter target   path. Flatten legacy tree depth in the Target IA Map.

### "Invalid character" / "reserved name" failures

Cause: Names containing SPO-invalid characters, trailing spaces/dots, or reserved leaf names.

Resolve: Rename at source per Remediation Plan – Source – PreMigration, or confirm the tool's

rename-on-ingest behavior in its current docs and enable it. Don't assume the tool auto-fixes —   verify.

### Assessment misses subtrees ("access denied")

Cause: The migration account lacks read/ACL-read on some folders.

Resolve: Grant the account read + ACL-read across the whole in-scope tree (Requirements §1) and

re-run; an incomplete assessment yields an incomplete permission map.

__________________________________________________

## Permission mapping

### `SPOMIG-PermissionMap.ps1` reports unmatched principals

Cause: Source NTFS/SP principals (local groups, deleted accounts, un-synced identities) don't

resolve to Entra ID objects.

Resolve: Complete directory sync for the population, replace local/stale groups with Entra

groups, and make a decision for each unmatched principal — never migrate it as a guess. The wave   gate requires zero unmatched.

### Day-one over-share or lockout after cutover

Cause: A principal mapped to too broad a group (over-share) or a mapped group missing on the

target (lockout).

Resolve: Re-check Permission Map – Source→SPO – Design, prefer scoped groups over "Everyone"

/ broad groups, re-apply, and re-run the validation permission spot-check (Testing §9).

__________________________________________________

## Migration execution (Migration Manager / SPMT)

### The delta pass re-copies everything instead of only changes

Cause: The incremental pass isn't the same task/mapping as the pre-stage, so the tool treats

it as a new full migration.

Resolve: Reuse the identical task (Migration Task – <Scope> – Wave<N>) and destination for the

delta; incremental only works against the same task identity.

### `SPOMIG-TaskBuilder.ps1` moved nothing / built only a CSV

Cause: That is the safe default — it dry-runs (build + validate) and does not start a

migration without -Commit.

Resolve: After validating the CSV, re-run with -Commit to Register-SPMTMigration /

Start-SPMTMigration. If it still won't start, confirm the   Microsoft.SharePoint.MigrationTool.PowerShell module is installed and sign-in succeeded.

### Migration Manager agent shows offline / tasks stuck

Cause: The agent host lost line-of-sight to the source (SMB / on-prem SP) or to SPO (443), or the

agent service stopped.

Resolve: Confirm the agent is online/healthy in the SharePoint admin center, the host can

reach both source and SPO endpoints (verify the current endpoint list for your cloud), and scale to   multiple agents for throughput on large estates.

### Throttling / slow throughput mid-wave

Cause: SPO service throttling under heavy concurrent load, or a single overloaded agent.

Resolve: Spread load across more agents, migrate during off-peak windows, and let the tool's

built-in retry/backoff run. Don't fight throttling with more parallelism on one host.

### Some files skipped: blocked type / oversized / in-use

Cause: Files exceeding the SPO file-size limit, on the blocked-file-type list, or locked/open at

scan time.

Resolve: These should have surfaced in assessment — reconcile against

Source Assessment – FileShare+SP – Discovery, remediate (archive/split/close), and re-run the   delta. IRM/RMS-protected or encrypted files may need vendor handling (deferred to vendor docs).

__________________________________________________

## Validation & cutover

### Target item count is lower than source

Cause: Legitimate filtered content (system files, blocked types) or genuinely missed items.

Resolve: SPOMIG-Validation.ps1 reports both counts; subtract the intended filter set — if a

gap remains, inspect the tool's per-item report for the missing items and re-run the delta before   passing the gate (Testing §8).

### Versions or metadata didn't come across as expected

Cause: The migration settings (version-history depth, metadata options) didn't match the

design.

Resolve: Confirm the tool's settings against the design, re-run for the affected scope. Verify

the exact setting names/behavior in the tool's current docs (they change).

### Users still editing the source after cutover ("split-brain")

Cause: The source wasn't actually set read-only at the delta/cutover window.

Resolve: Enforce read-only on the source at cutover per Cutover Plan – <Scope> – Wave<N>, re-run

the delta to capture stragglers, then redirect users. Keep the source read-only (not deleted) until   the wave gate passes.

__________________________________________________

## Government / sovereign cloud

### A step or tool behaves differently in GCC High / DoD

Cause: Sovereign clouds (*.sharepoint.us / *.office365.us) can differ in tool support,

endpoints, and limits.

Resolve: Verify in your tenant — confirm the tool supports your cloud, use the correct

endpoints, and re-confirm limit values; do not assume Commercial behavior.

# 7. Best Practices — File-Share & On-Prem SharePoint → SharePoint Online Migration

Durable practices for migrating file shares and on-prem SharePoint into SharePoint Online cleanly.

## Assess before you move — always

Never migrate un-assessed content. Path/URL length, invalid characters, blocked file types, and

oversized files fail *during* the migration; find them in assessment, not at scale on cutover night.

Track Microsoft's limits as live values, not memorized constants. SPO service limits change and

differ by cloud (Commercial vs Government / sovereign). Feed the *current* documented values into   SPOMIG-Assessment.ps1 as parameters and re-confirm per engagement.

Measure the permission surface early. The number of distinct principals in the source ACLs

predicts how hard the permission map will be — surface it in assessment so it isn't a surprise.

## Design a target, don't mirror the source

Map to a governed IA; don't pave the cow paths. Migration is the one chance to flatten deep

trees, retire dead shares, and land content where it belongs. Mirroring drive letters wastes it.

Every target site has an owner and a sharing posture before content lands. Migrating into an

ungoverned site creates orphans on day one.

Name everything once with <Purpose> – <Scope> – <Stage> and reuse the names across the

assessment, map, tasks, validation, and cutover plan — traceability from source path to destination   URL is what makes validation possible.

## Permissions: map to groups, resolve every principal

Prefer SPO/M365/Entra groups over individuals. Individual ACEs migrated verbatim recreate the

unmanageable sprawl you're trying to escape.

Resolve unmatched principals with a decision, never a guess. An unmapped principal either

over-shares or locks people out — both are day-one incidents. SPOMIG-PermissionMap.ps1 flags them   so they get a decision.

Break-permission inheritance sparingly in the target. Re-establish clean inheritance where the

legacy source had ad-hoc unique permissions everywhere.

## Migrate with pre-stage + delta — keep downtime tiny

Pre-stage while the source is live, delta at cutover. Do the slow bulk copy with users still

working; freeze the source read-only only for the short incremental pass. This turns a multi-day   freeze into hours.

Reuse the same task for the delta. Incremental only works when the delta pass is the *same*

task/mapping as the pre-stage — a new task re-copies everything.

Scale throughput with multiple agents (Migration Manager) for large estates rather than one

overloaded host; measure and right-size.

Never set the source read-only before pre-stage completes — the freeze belongs at the delta/

cutover moment, not before.

## Validate every wave — evidence, not optimism

Counts + permissions + delta-clean + governed is the gate. A wave isn't done because the tool

said "complete"; it's done when the validation report proves it.

Spot-check permissions in the real UI, not just the tool's log — confirm no broad group crept

in and every mapped group is present.

Keep the source authoritative until the gate passes and a soak period ends. The source read-only

copy is your rollback; don't destroy it early.

## Safety and secrets

Read-only by default; writes gated behind `-Commit`. Assessment, permission-mapping, scope-

health, and validation change nothing. Task execution moves data only on explicit -Commit.

No hardcoded credentials. Use modern-auth Connect-PnPOnline / Connect-SPOService /

Register-SPMTMigration interactive or app-registration sign-in; never embed secrets in the   scripts or the CSVs.

Least-privilege migration account. Grant only the source read/ACL-read and the target

contribute/owner the migration needs; don't run migrations as a tenant Global Admin by default.

## Compliance stays with compliance

Technical method, not legal determination. What to retain, what's under legal hold, and which

records schedule applies are decided by the compliance/records/legal functions. This solution   supplies the migration method and the evidence; the *decision* to delete or archive a retired source   is theirs.

## Government and sovereign clouds

Verify, don't assume. GCC High / DoD (*.sharepoint.us / *.office365.us) and other sovereign

clouds can differ in tool support, endpoints, and limits. Confirm each in your tenant before   planning a wave there.

# 8. Deliverables Summary — File-Share & On-Prem SharePoint → SharePoint Online Migration

Everything included in this solution, on one page.

## Documentation

01 · Solution Overview — the migration model (assess/remediate, target IA mapping, tool options,

pre-stage/delta, permissions, validation), the reference design, benefits, limitations, and the   Assess → Design → Configure → Pilot → Validate → Expand deployment model.

02 · Requirements — the seven migration-specific prerequisites (source access, migration

workstation/agent, tool choice, target IA, storage + service-limit check, identity mapping, cutover   window) that build on the shared SharePoint global requirements.

03 · Implementation — exact ordered steps: assess → remediate + design target IA + permission

map → configure the tool → pilot pre-stage/delta → validate (gate) → expand wave by wave. Every   artifact named; pass/fail gates and rollback included.

05 · Testing & Validation — ten tests, each with pass/fail signals, culminating in the wave gate

(counts + permissions + delta-clean + governed).

06 · Troubleshooting — the common failure modes (blocked items, permission mismatches, delta

re-copies, agent/throughput, throttling, identity gaps) and their resolutions.

07 · Best Practices — durable practices for assessment, target design, permission mapping,

pre-stage/delta cutover, validation, safety, and government-cloud verification.

Executive Summary — outcome, approach, and why the migration is low-risk.

## PowerShell tools (5) — read-only or dry-run by default, no credentials in code

SPOMIG-Assessment.ps1 — *Source assessment (read-only).* Scans a file share (and inventories

on-prem SP content passed in) for the blockers that fail SPO migrations — path/URL length near the    limit, invalid characters/reserved names, blocked file types, oversized files, deep nesting — and    summarizes the permission surface. Emits Source Assessment – FileShare+SP – Discovery. Current    SPO limits are passed as parameters so the check tracks Microsoft's real numbers. Makes no changes.

SPOMIG-PermissionMap.ps1 — *Permission-mapping helper (read-only).* Enumerates source

principals (NTFS/SP groups, ACEs) and proposes a target mapping to SPO/M365/Entra groups with a    permission level, flagging unmatched principals for a decision. Emits Permission Map –    Source→SPO – Design. Plans only; changes nothing.

SPOMIG-TaskBuilder.ps1 — *SPMT task/CSV builder + runner (safe-by-default).* Turns

Target IA Map – SPO – Design into a migration bulk CSV and validates it (dry-run by default);    only registers and starts the SPMT migration when -Commit is passed. Uses the    Microsoft.SharePoint.MigrationTool.PowerShell module with modern-auth sign-in.

SPOMIG-Validation.ps1 — *Post-migration validation (read-only).* Compares source vs. target

item counts and spot-checks permissions against the permission map via PnP PowerShell.    Emits Post-Migration Validation – <Scope> – Validate — the evidence for the wave gate.

SPOMIG-ScopeHealth.ps1 — *Scope/config health helper (read-only).* Verifies the target site

exists and is writable, storage is sufficient, and the migration prerequisites are green before    tasks are defined. Reports only.

## Named artifacts (created during implementation)

Source Assessment – FileShare+SP – Discovery · Remediation Plan – Source – PreMigration · Target IA Map – SPO – Design · Permission Map – Source→SPO – Design · Migration Task – Pilot – Wave0 · Migration Task – <Scope> – Wave<N> · Cutover Plan – <Scope> – Wave<N> · Post-Migration Validation – <Scope> – Validate · SPO Site – Pilot – Prod

# Appendix A — PowerShell Scripts

The following scripts are included in the accompanying ZIP. Each script's own header documents its full usage and expected results.

## SPOMIG-Assessment.ps1

## SPOMIG-PermissionMap.ps1

## SPOMIG-ScopeHealth.ps1

## SPOMIG-TaskBuilder.ps1

## SPOMIG-Validation.ps1