CloudM Migrate — M365 → Google Migration Execution

Implementation Solution Guide

Version 1.0.0    ·    2026-07-06

# Contents

Right-click and choose “Update Field” to build the table of contents.

# Executive Summary

## Outcome

Microsoft 365 mail, files, and collaboration data are migrated to Google Workspace reliably and with minimal user disruption, using CloudM Migrate as the migration engine. Each cohort of users is moved, validated against an explicit set of gates, and cut over on a controlled schedule — so the organization completes its M365→Google migration at scale without the surprises of an unplanned cutover.

## Approach

The solution is an execution playbook, not a tool manual. It follows the house model Assess → Design → Configure → Pilot → Validate → Expand:

Configure the CloudM platform (hosted or self-hosted) and authenticated connections to M365

(Entra app registration, source) and Google Workspace (service account with domain-wide delegation,   destination).

Build a reusable migration profile and a source→destination user list.

Run the proven pass sequence — Scan (discover), Pre-stage (bulk historical copy), Full/Delta

(incremental), Cutover (mail-routing switch), post-cutover Delta — wave by wave, department by   department.

Validate every wave against pass/fail gates (item-count reconciliation, permissions, mail flow)

before it is closed.

Five Python tools automate the safe, repeatable parts — readiness assessment, user-list generation, wave/throttling planning, post-migration validation reporting, and health monitoring — all read-only or dry-run by default, with no credentials in code.

## Why it is low-risk

Pilot-first with hard gates. Nothing goes to production until a pilot wave passes end-to-end

validation. A failed wave is contained to its cohort.

Pre-staging shrinks the cutover. The bulk of data moves days ahead of the change window, so the

final switch is small, fast, and reversible.

Documented rollback on every high-impact change. Mail-routing/DNS cutover runs under change

control with a pre-agreed revert to M365; the source stays authoritative until validation passes.

Vendor boundaries respected. Google and Microsoft/Entra steps are exact and current; CloudM

console internals, licensing, and fidelity specifics are deferred to CloudM's own documentation, so   the playbook stays accurate as the tool evolves.

Bottom line: M365→Google migrations completed reliably on CloudM — platform connected, profiles built, pre-stage and delta passes run and validated — with minimal disruption at enterprise scale, at a fraction of full-consulting cost.

# Solution Overview

## What this solution is

This solution is the execution playbook for migrating Microsoft 365 to Google Workspace using CloudM Migrate at enterprise scale. It covers the end-to-end procedure — standing up the CloudM platform (hosted or self-hosted), building the M365 and Google connections, designing the migration profile and user list, and running the scan / pre-stage / full / delta sequence with throttling and validation — so that mail, files, and collaboration data move reliably with minimal user disruption.

CloudM Migrate is a third-party migration engine. This document treats it at the procedural playbook level: architecture, prerequisites, connection/endpoint setup, profile and mapping design, wave and pre-stage/delta sequencing, throttling, and validation. Deep CloudM console internals, exact screen labels, licensing tiers, and product support are deferred to CloudM's own documentation — where a step depends on a specific CloudM version or a preview behavior, it is flagged "verify for your version." The Google Admin console / Cloud Identity side and the Microsoft 365 / Entra side are authored at exact detail because they are stable, publicly documented platforms.

## How it works

CloudM Migrate reads from a source (Microsoft 365 — Exchange Online mailboxes, OneDrive, and SharePoint) and writes to a destination (Google Workspace — Gmail, Google Drive, Shared Drives) over each vendor's APIs. The migration is driven by four moving parts:

Platform — the CloudM Migrate engine, either hosted (CloudM-run SaaS) or self-hosted

(installed on your own Windows migration server[s], scaled out for throughput). The engine holds    the migration configuration and executes the passes.

Connections — authenticated links to each ecosystem: a **Microsoft 365 / Entra app

registration (source read) and a Google Workspace service account / OAuth** with    domain-wide delegation (destination write). These are the security identities the engine acts as.

Migration profile — the reusable configuration object that says *what* to migrate (mail,

calendar, contacts, Drive/OneDrive, SharePoint), *how* to map source users to destination users,    filtering (date ranges, folder exclusions), and throttling limits.

User list — the CSV of source→destination mappings that scopes each run to a set of users

(and, for files, sites/paths → Shared Drives).

The engine runs in passes: a Scan (read-only discovery of item counts and sizes), an optional Pre-stage (bulk-copy the historical bulk of data ahead of cutover while users still work in M365), a Full pass, and repeated Delta passes (copy only what changed since the last pass) leading up to cutover (MX/mail-routing switch to Google). A final delta after cutover sweeps any last items.

## Reference model — naming convention

Every artifact this solution creates is named with the convention <Purpose> – <Scope> – <Stage> and that exact name is reused in later steps, testing, troubleshooting, and the scripts:

| Artifact | Example name | What it is |
| --- | --- | --- |
| CloudM platform instance | Migration Platform – Enterprise – Prod | The hosted/self-hosted engine |
| M365 source connection | Source Connection – M365 – Prod | Entra app registration used as source |
| Google destination connection | Destination Connection – Google – Prod | GCP service account w/ DWD |
| Migration profile | Migration Profile – Mail+Drive – Standard | Reusable what/how config |
| Pilot wave | Migration Wave – Pilot – Wave0 | First validated cohort (25–50 users) |
| Production wave | Migration Wave – Finance – Wave3 | A departmental cohort |
| Pre-stage run | Pre-stage Run – Finance – Wave3 | Bulk historical copy pre-cutover |
| Delta run | Delta Run – Finance – Wave3 | Incremental changed-items copy |
| Validation report | Validation Report – Finance – Wave3 | Post-migration item/permission check |

## Where CloudM Migrate fits vs. native and other tools

Native / Google-first: Google's own Data Migration Service (mail only, small scale) and

GWMME / Google Workspace Migrate handle certain M365→Google moves. CloudM Migrate is chosen for   breadth (mail + Drive + SharePoint + collaboration in one engine), scale (parallelism,   self-hosted throughput), and operational tooling (per-user reporting, retriable deltas).

Other third-party engines: BitTitan MigrationWiz and Google Workspace Migrate solve overlapping

problems; the engine choice is an architecture decision made before this playbook runs. This   solution assumes CloudM Migrate has been selected.

## The wave approach

Migration is executed wave by wave, never fleet-wide in one shot. Each wave is a cohort of users (typically aligned to a department or site) that flows through pre-stage → delta → cutover → post-cutover delta → validate. The pilot wave (Migration Wave – Pilot – Wave0) proves the profile and connections end-to-end before any production wave runs.

## Benefits

Reliable, repeatable cutovers — pre-staging historical data moves the bulk of bytes off the

cutover critical path; deltas keep the final switch small and fast.

Minimal disruption — users keep working in M365 until their wave cuts over; only the small

final delta happens during the change window.

Auditable — every wave produces a validation report (item counts, permissions, mail-flow) with

explicit pass/fail gates.

Scoped risk — pilot-first with documented rollback; a bad wave is contained to its cohort.

## Limitations & boundaries

Fidelity is engine- and API-bound. Some item types migrate with reduced fidelity (e.g. certain

Exchange rules, SharePoint web parts, complex OneNote); confirm the current fidelity matrix in   CloudM's documentation for your version.

This is not a CloudM console manual. Screen-by-screen console navigation, licensing, and

entitlement are CloudM's to document; verify for your version.

Throttling is provider-imposed. Microsoft Graph / Exchange and Google API quotas cap

throughput; this solution gives sequencing and throttling *guidance*, not guaranteed rates.

Coexistence (free/busy, mail routing during migration) is adjacent and may need its own design;

this solution focuses on data movement and cutover.

## Deployment model

This solution follows the house model: Assess → Design → Configure → Pilot → Validate → Expand, pilot-first, with explicit pass/fail gates and a documented rollback for every high-impact production change (mail flow, DNS/MX, sharing, cutover). No production wave proceeds until the pilot wave passes its validation gate.

# Requirements

These are the solution-specific prerequisites for executing an M365→Google migration with CloudM Migrate. They build on the shared [Global Requirements — Google Workspace & Gemini Solutions](global-requirements-google.md), which cover the baseline every Google-category solution assumes: a provisioned Google Workspace / Cloud Identity tenant with super-admin (GR-1), the source Microsoft 365 / Entra environment with admin access (GR-2), DNS control for the routed domains (GR-3), an identity source of truth and provisioning model (GR-4), a pilot OU/group and change control (GR-5), and security/compliance stakeholders (GR-6). Verify those first; the prerequisites below are additive and CloudM/migration-specific.

Vendor boundary reminder. CloudM platform capabilities, licensing, and console internals are deferred to CloudM's own documentation and flagged "verify for your version." The Google and Microsoft/Entra items below are authored at exact detail from the vendors' public docs.

__________________________________________________

## R1. CloudM Migrate platform provisioned (hosted or self-hosted)

Description: A licensed CloudM Migrate environment. Either hosted (CloudM-run SaaS) or

self-hosted on one or more Windows migration servers sized for the workload. Name the instance   Migration Platform – Enterprise – Prod.

Why required: The platform is the engine that holds the migration configuration and executes

scan/pre-stage/delta passes. Nothing runs without it.

How to verify: Sign in to the CloudM Migrate platform and confirm you can reach the migration

configuration area and that your license covers M365→Google mail + files (and SharePoint if in   scope). Verify edition, license counts, and feature coverage in CloudM's licensing docs — deferred   to CloudM.

How to implement if missing: Procure the license and stand up the platform per CloudM's

deployment guide. For self-hosted, provision the migration server(s) meeting CloudM's stated OS,   CPU/RAM, and .NET/runtime prerequisites (verify current sizing and prerequisites for your   version), on a network with outbound HTTPS to both Microsoft and Google API endpoints.

## R2. Microsoft 365 source app registration (Entra ID)

Description: An Entra ID app registration that CloudM authenticates as to read the source:

Exchange Online mailboxes, OneDrive, and SharePoint. Name it Source Connection – M365 – Prod.

Why required: CloudM reads source data over Microsoft Graph and Exchange APIs; a properly

consented app registration (or the app-based access CloudM's connector documents) is the source   identity.

How to verify: In the Entra admin center → App registrations, confirm the app exists, has

the application permissions CloudM's M365 connector requires (typically Graph mail/files/sites   read plus Exchange access), and that admin consent has been granted (green check under API   permissions). Confirm the client secret/certificate is current and stored securely. The exact   permission scopes are defined by CloudM's connector docs — verify for your version.

How to implement if missing: Create the app registration (**Entra admin center → App

registrations → New registration), add the API permissions CloudM specifies, Grant admin   consent for the tenant**, and create a client secret or upload a certificate. Record the   Application (client) ID, Directory (tenant) ID, and secret/cert into the CloudM connection — never   into source-controlled files.

## R3. Google Workspace destination service account with domain-wide delegation

Description: A Google Cloud service account with domain-wide delegation (DWD) authorized

in the Google Admin console for the OAuth scopes CloudM's Google connector requires (Gmail insert,   Drive, Calendar, Contacts, Directory read). Name it Destination Connection – Google – Prod.

Why required: CloudM writes migrated data into each destination user's Gmail/Drive by

impersonating them; DWD is the mechanism that authorizes that impersonation tenant-wide.

How to verify: In Google Cloud console → IAM & Admin → Service Accounts, confirm the account

and its key exist and DWD is enabled. In admin.google.com → Security → Access and data control →   API controls → Domain-wide delegation, confirm the service account's client ID is present with   the required scopes listed. Confirm the exact scope list against CloudM's Google connector docs —   verify for your version.

How to implement if missing: Create the service account and a JSON key in Google Cloud; enable

DWD; then in the Admin console add the service account Client ID under Domain-wide delegation   with the CloudM-specified OAuth scopes (comma-separated). Also enable the required APIs (Gmail,   Drive, Admin SDK, Calendar, People) in the Cloud project. Store the JSON key in the CloudM   platform's secured credential store — never in the repo.

## R4. Destination users and Shared Drives provisioned

Description: The destination Google Workspace accounts for the wave's users exist and are

licensed, and any Shared Drives that will receive SharePoint/team content are created and named   (<Team> Shared Drive). Provisioning flows from the identity source of truth (GR-4) via GCDS/SCIM.

Why required: CloudM writes into existing destination mailboxes/Drives; missing or unlicensed

target accounts cause per-user failures.

How to verify: In admin.google.com → Directory → Users, confirm the wave's target accounts

exist and are licensed. In Shared drives, confirm the target Shared Drives exist.

How to implement if missing: Provision users via GCDS/SCIM from the source of truth; assign

licenses; pre-create Shared Drives for team/SharePoint destinations.

## R5. Source→destination mapping (user list CSV)

Description: A user-list CSV mapping each source M365 identity (UPN/primary SMTP) to its

destination Google address, plus any file source→Shared Drive mappings. This is the artifact CloudM   consumes to scope a run. (The included build-migration-userlist.py tool generates a   connector-agnostic version of this from the Google directory + a source export — align the final   column headers to CloudM's import template for your version.)

Why required: CloudM scopes each scan/pre-stage/delta pass to the users in the list; an

incorrect mapping migrates data to the wrong account.

How to verify: Confirm every source UPN resolves to exactly one destination address that exists

in the Google directory, and that there are no duplicates or unmapped rows.

How to implement if missing: Export the source user list from M365/Entra, reconcile against the

Google directory, and produce the mapping CSV (the tool assists). Review with the identity owner   before import.

## R6. Migration profile design decided

Description: A documented decision on what each wave migrates (mail incl. date-range filter,

calendar, contacts, OneDrive, SharePoint), fidelity expectations, throttling limits, and   exclusions (e.g. Recoverable Items, huge archives). Captured as Migration Profile –   Mail+Drive – Standard.

Why required: The profile is the reusable contract for every wave; deciding it once keeps waves

consistent and makes pre-stage/delta behavior predictable.

How to verify: Confirm the profile choices are written down and approved by the migration and

security owners (retention/eDiscovery implications per GR-6).

How to implement if missing: Run a design workshop to set scope, filters, and throttling; record

the decisions; then build the profile in CloudM (console steps deferred to CloudM docs).

## R7. Change window, cutover plan, and rollback

Description: An approved change window for each wave's MX/mail-routing cutover (GR-3

DNS), a written cutover runbook, and a documented rollback (revert MX, keep M365 authoritative)   should validation fail.

Why required: Cutover changes mail flow — the highest-impact change in the project. Rollback must

be pre-agreed, not improvised.

How to verify: Confirm the change ticket, window, approvers, and rollback steps exist for the

wave.

How to implement if missing: Draft the cutover runbook and rollback, route through change

control (GR-5), and get sign-off before the wave's cutover.

# Global Requirements — Google Workspace & Gemini Solutions

These requirements apply to every solution in the Google category. They are the common foundation each Google Workspace / Gemini solution assumes is already in place (or stands up as part of its own Requirements section). Verify each before starting a solution's implementation steps.

Vendor boundary (applies to every Google solution). The Google Admin console (admin.google.com), Google Cloud / Cloud Identity, and the Microsoft / Entra sides are authored at exact, current click-by-click detail from the vendors' public documentation. Gemini Enterprise capabilities that are in preview or rolling out are cited or flagged "verify in your tenant" — never invented. Third-party migration tools (e.g. for mail/Drive/Chat data movement) and third-party enterprise apps (ServiceNow, SAP, Databricks, etc.) are integrated at the pattern/architectural level; their internal console steps are deferred to the vendor's own docs.

## 1. Google Workspace / Cloud Identity tenant

Description: A provisioned Google Workspace (or Cloud Identity) tenant with a super-admin

account for configuration, and the appropriate Workspace edition/licensing for the capability in   scope (e.g. Enterprise Plus for Vault/CAA/DLP, Gemini/AI add-on where required).

Why required: All configuration, policy, and API work is performed against this tenant.

How to verify: Sign in to admin.google.com as a super-admin; confirm edition and license

counts under Billing / Subscriptions.

How to implement if missing: Provision the tenant and licenses through Google or an authorized

reseller before starting.

## 2. Source Microsoft 365 / Entra environment (for migration & coexistence)

Description: For migration/coexistence/identity solutions, administrative access to the source

Microsoft 365 tenant and Microsoft Entra ID (Global Administrator or the least-privilege   roles the solution names).

Why required: Migration, directory sync, SSO federation, and coexistence read from and change

the Microsoft side.

How to verify: Confirm access to the M365 admin center and the Entra admin center with the

required role.

How to implement if missing: Obtain the role from the M365/Entra tenant owner.

## 3. DNS control for the routed domains

Description: Ability to create/modify DNS records (MX, SPF, DKIM, DMARC, TXT, CNAME) for the

domains being migrated, coexisting, or verified.

Why required: Domain verification, mail routing/coexistence, and authentication all depend on

DNS changes.

How to verify: Confirm access to the authoritative DNS zone for each domain.

How to implement if missing: Coordinate with whoever controls DNS; stage changes under change

control (mail-flow changes are high-impact).

## 4. Identity & provisioning source of truth

Description: A defined identity source of truth (on-prem AD, Entra ID, or an HR/IGA system)

and the sync mechanism (e.g. Google Cloud Directory Sync (GCDS) or SCIM-based provisioning).

Why required: Consistent users/groups across ecosystems underpin SSO, licensing, and access.

How to verify: Confirm which directory is authoritative and how objects flow into Google.

How to implement if missing: Define the source of truth and provisioning model before configuring

SSO or migrating.

## 5. A pilot scope (OU / group) and change control

Description: A pilot organizational unit or group to validate on before fleet-wide rollout,

and a change-control process for production changes (especially mail flow, DNS, identity, and DLP).

Why required: Every solution follows an Assess → Configure → Pilot → Validate → Expand model;

the pilot proves the design and change control protects production.

How to verify: Confirm a named pilot OU/group exists and a change window/approval path is available.

How to implement if missing: Create a pilot OU/group and agree the change-control process with the

owners before making production changes.

## 6. Security, compliance & governance stakeholders

Description: Engagement with the security (CISO), legal/eDiscovery, and data-governance

stakeholders whose policies the configuration must satisfy (DLP, retention, Vault/Purview, and any   regulatory regime such as ITAR/DFARS/Assured Controls where applicable).

Why required: Data governance, eDiscovery, DLP, and regulated-workload settings must align to

enterprise policy and legal requirements, not just technical defaults.

How to verify: Confirm the applicable policies and named stakeholders/approvers.

How to implement if missing: Identify the owners and obtain the policy/compliance requirements

before configuring governance controls.

*The deployment model across every Google solution is the same: Assess → Configure → Pilot → Validate → Expand, with explicit pass/fail gates and a documented rollback for production changes.*

# Implementation

Execute the migration following the house model Assess → Design → Configure → Pilot → Validate → Expand, pilot-first, with explicit pass/fail gates and a documented rollback. Every artifact is named with the <Purpose> – <Scope> – <Stage> convention and reused verbatim in testing, troubleshooting, and the scripts.

CloudM console internals are deferred to CloudM's documentation. Where a step happens *inside* the CloudM Migrate console (creating the connection object, building the profile, launching a run), the procedure and sequencing are given here; the exact screen labels and clicks are CloudM's to document and may change by version — verify for your version. Google Admin console and Entra steps are exact.

__________________________________________________

## Stage 1 — Assess (read-only discovery)

1.1 Inventory the source. Run assess-migration-readiness.py (read-only) against the Google destination directory and a source export to size the migration: user counts, mailbox and OneDrive sizes, SharePoint site inventory, and license coverage. Save the output as the assessment baseline.

1.2 Confirm quotas and endpoints. Confirm the Google project has the required APIs enabled and that both Microsoft and Google API endpoints are reachable from the platform's network (self-hosted: from each migration server). Record the provider throttling ceilings you expect to hit (Graph per-app/per-mailbox limits, Gmail API quotas) — plan-migration-waves.py uses these to advise throttling.

1.3 Verify all requirements. Walk R1–R7 and the global GR-1…GR-6. Gate 1 (Assess): every requirement verified, assessment baseline captured. Do not proceed until met.

## Stage 2 — Design

2.1 Design waves. Group users into waves aligned to departments/sites. Reserve Migration Wave – Pilot – Wave0 (25–50 low-risk, cooperative users spanning the data types you must prove: heavy mailbox, large OneDrive, Shared-Drive/SharePoint user). Run plan-migration-waves.py to produce a sequenced wave plan with pre-stage/delta ordering and throttling guidance.

2.2 Design the profile. Finalize Migration Profile – Mail+Drive – Standard per R6: what to migrate, date-range filters, exclusions, fidelity expectations, and throttling limits.

2.3 Design the user list. Generate the mapping CSV with build-migration-userlist.py (dry-run default), reconciling source UPNs to destination Google addresses and file sources to Shared Drives. Align headers to CloudM's import template (verify for your version).

Gate 2 (Design): wave plan, profile design, and pilot user list reviewed and approved by the migration + security owners.

## Stage 3 — Configure

3.1 Stand up the platform. Confirm Migration Platform – Enterprise – Prod is reachable (hosted) or installed/scaled (self-hosted) per R1.

3.2 Build the source connection. In CloudM, create Source Connection – M365 – Prod using the Entra app registration from R2 (Application/Directory IDs + secret/cert). *(CloudM console steps deferred — verify for your version.)* Test the connection; it must authenticate and enumerate a sample mailbox.

3.3 Build the destination connection. Create Destination Connection – Google – Prod using the service account + DWD from R3. Test; it must authenticate and impersonate a sample destination user. If it fails, re-check the DWD scope list in admin.google.com → Security → API controls → Domain-wide delegation (see Troubleshooting).

3.4 Build the profile. Create Migration Profile – Mail+Drive – Standard from the R6 design.

3.5 Import the pilot user list. Import the Migration Wave – Pilot – Wave0 CSV into a run bound to the profile.

Gate 3 (Configure): both connections test green; profile and pilot list imported without errors.

## Stage 4 — Pilot (`Migration Wave – Pilot – Wave0`)

Run the full pass sequence on the pilot cohort. This proves the design before any production wave.

4.1 Scan (read-only). Launch a Scan pass for Wave0. It discovers item counts/sizes per user without writing. Record the scan totals as the expected baseline for validation.

4.2 Pre-stage. Launch Pre-stage Run – Pilot – Wave0 to bulk-copy historical mail and files into Google while pilot users still work in M365. Monitor throughput; if you hit provider throttling, lower concurrency per plan-migration-waves.py guidance (see Troubleshooting).

4.3 Delta + cutover. In the approved change window (R7):

Run Delta Run – Pilot – Wave0 to copy everything changed since pre-stage.

Execute the MX/mail-routing cutover for the pilot users' domain/routing per the cutover

runbook (DNS is high-impact — GR-3).

Run a post-cutover Delta Run – Pilot – Wave0 to sweep the final items delivered to M365

during the switch.

Gate 4 (Pilot pass/fail): proceed to validation only if all pilot users completed with errors triaged (not necessarily zero, but every error explained). Rollback if failed: revert MX to M365, keep M365 authoritative, retriage, and re-run — no production wave starts until the pilot passes.

## Stage 5 — Validate

5.1 Run validation. Execute Validation Report – Pilot – Wave0 with validate-migration-report.py: compare migrated item counts against the scan baseline per user, spot-check Drive/Shared-Drive permissions, and confirm mail is delivering to Google (test message in/out). See 05-testing.md for the full test matrix and expected results.

5.2 Confirm mail flow. Send a message from an external address to a pilot user and confirm delivery to Gmail; send from the pilot user outbound and confirm SPF/DKIM/DMARC pass.

Gate 5 (Validate): item-count variance within the agreed tolerance, permissions intact, mail flowing both ways, users confirm access. Only now is the profile/connection design blessed for production.

## Stage 6 — Expand (production waves)

For each production wave (e.g. Migration Wave – Finance – Wave3), repeat the proven sequence:

Import the wave's user list into a run on Migration Profile – Mail+Drive – Standard.

Scan → record baseline.

Pre-stage Run – <Dept> – <Wave> well ahead of the change window.

In the change window: Delta Run → MX cutover (per runbook, rollback ready) → post-cutover

Delta Run.

Validation Report – <Dept> – <Wave> — must pass the Gate 5 criteria before the wave is closed.

Sequence waves per plan-migration-waves.py so concurrent pre-stage/delta load stays under provider throttling ceilings. Run check-migration-health.py between passes to watch error rates, throttling signals, and destination account/license health, and to catch drift before it compounds.

Per-wave rollback (production): if a wave fails validation, revert its MX/routing to M365, keep M365 authoritative for that cohort, triage errors, and re-run the delta+cutover in the next window. Because waves are cohort-scoped, a failure is contained.

# Testing & Validation

Each wave must pass these validations before it is closed. Run them at the pilot (Migration Wave – Pilot – Wave0) first, then for every production wave. Where a test is scripted, the tool is named. Record results in the wave's Validation Report – <Scope> – <Stage>.

Item-count variance is measured against the Scan baseline captured before the pre-stage pass. Agree a tolerance up front (e.g. ≤0.5% per user, with any excluded item types — Recoverable Items, filtered date ranges — subtracted from the expected count so the comparison is apples-to-apples).

__________________________________________________

## T1. Connection authentication

Procedure: In CloudM, test Source Connection – M365 – Prod and

Destination Connection – Google – Prod.

Expected PASS: both authenticate; source enumerates a sample mailbox; destination impersonates a

sample destination user.

FAIL: auth error or impersonation denied → see Troubleshooting (app-consent / DWD scope

mismatch).

## T2. Scan baseline captured

Procedure: Confirm the Scan pass completed for every user in the wave and totals were recorded.

Expected PASS: per-user item counts and sizes recorded for mail, OneDrive, and SharePoint in

scope; zero users failed to scan.

FAIL: any user missing a scan total → resolve access for that user before pre-stage.

## T3. Item-count reconciliation (mail + files)

Procedure: Run validate-migration-report.py to compare destination item counts (Gmail

messages via Gmail API; Drive files via Drive API) against the Scan baseline, per user, after the   final post-cutover delta.

Expected PASS: per-user variance within the agreed tolerance for every user in the wave;

variances explained by known exclusions.

FAIL: any user over tolerance → triage in Troubleshooting (incomplete items / throttling

truncation), re-run delta, re-validate.

## T4. Drive & Shared Drive permissions

Procedure: With validate-migration-report.py --check-permissions, spot-check a sample of

migrated Drive items and Shared Drives: sharing/membership matches the intended mapping.

Expected PASS: sampled items have the expected members/roles; no unexpected public/"anyone"

sharing was introduced.

FAIL: permission drift or over-sharing → correct sharing, review the profile's permission

handling (verify CloudM permission-mapping behavior for your version).

## T5. Mail flow after cutover

Procedure: Send an inbound test (external → migrated user) and an outbound test (migrated user →

external) after the MX cutover.

Expected PASS: inbound lands in Gmail; outbound passes SPF, DKIM, and DMARC (check the

received-message authentication results).

FAIL: non-delivery or auth failure → check MX/DNS records and SPF/DKIM/DMARC alignment for the

domain (high-impact — treat under change control).

## T6. Calendar & contacts fidelity

Procedure: Spot-check a sample of migrated calendars and contacts against the source.

Expected PASS: future meetings, recurrence, and key contacts present; known-reduced-fidelity

items match CloudM's documented fidelity matrix.

FAIL: missing future meetings → re-run with calendar in scope; document any vendor-known

fidelity gaps.

## T7. Error triage completeness

Procedure: Review the wave's per-user error report; run check-migration-health.py for the

aggregate error/throttling picture.

Expected PASS: every error is either resolved or explicitly accepted with a reason; no

unexplained failures.

FAIL: unexplained errors remain → do not close the wave; resolve or formally accept each.

## T8. User acceptance (pilot)

Procedure: Pilot users confirm they can access mail, calendar, and files in Google and that

recent items are present.

Expected PASS: pilot users sign off; no blocking access issues.

FAIL: blocking issue → invoke pilot rollback (revert MX, M365 authoritative), fix, re-run.

__________________________________________________

### Wave close gate

A wave is closed only when T1–T7 PASS (and T8 for the pilot). Any FAIL routes to Troubleshooting, a corrective delta re-run, and re-validation — or, for a cutover-level failure, the documented rollback.

# Troubleshooting

Common failure modes when executing an M365→Google migration with CloudM Migrate, and how to resolve them. Named artifacts (Source Connection – M365 – Prod, Destination Connection – Google – Prod, Migration Profile – Mail+Drive – Standard, Migration Wave – <Scope> – <Stage>) refer back to Implementation and Testing.

CloudM console specifics are deferred to CloudM's documentation. Where a fix lives inside the CloudM console, the *symptom and direction* are given here; exact clicks and version behavior are CloudM's to document — verify for your version.

__________________________________________________

## Connections & authentication

### `Destination Connection – Google – Prod` fails to authenticate / impersonate

Symptom: Connection test fails, or per-user writes fail with unauthorized_client /

impersonation denied.

Cause: Domain-wide delegation (DWD) scope mismatch or missing API enablement.

Fix: In **admin.google.com → Security → Access and data control → API controls → Domain-wide

delegation, confirm the service account Client ID is present and its scope list exactly   matches CloudM's Google connector requirements (a single missing scope fails impersonation). Confirm   the Cloud project has Gmail, Drive, Admin SDK, Calendar, and People APIs enabled**. Re-test.   validate-migration-report.py uses the same DWD path — if it errors on with_subject, the grant is   the likely culprit.

### `Source Connection – M365 – Prod` fails

Symptom: Source test fails to authenticate or cannot enumerate mailboxes.

Cause: Entra app registration missing admin consent, missing permissions, or an expired

secret/certificate.

Fix: In Entra admin center → App registrations → your app → API permissions, confirm the

permissions CloudM's M365 connector requires are present and show admin consent granted (green   check). Confirm the client secret/certificate has not expired; rotate if needed and update the   CloudM connection (never store the secret in the repo).

## Throttling & API limits

### Throughput collapses / many 429 / backoff during pre-stage or delta

Symptom: Passes slow dramatically; run log shows HTTP 429, "rate limit", "too many requests".

Cause: Microsoft Graph/Exchange or Gmail/Drive provider throttling — expected under high

concurrency.

Fix: Lower concurrency, don't retry blindly. Start from the ceiling

plan-migration-waves.py recommends and halve it on repeated throttling. Keep total simultaneous   user migrations across all running waves under the ceiling. Shift pre-stage to off-hours. Run   check-migration-health.py --run-log <export> to quantify throttling signals before re-running.

### One user or mailbox is disproportionately slow

Symptom: A single very large mailbox/OneDrive stalls a wave.

Cause: Per-mailbox provider limits and item volume.

Fix: Pre-stage large mailboxes early and separately (flagged by

assess-migration-readiness.py --large-mailbox-gb); consider date-range filtering in the profile for   the deepest archives (record the exclusion so validation tolerance accounts for it).

## Item counts & delta issues

### Item-count variance over tolerance in `Validation Report – <Scope> – <Stage>`

Symptom: validate-migration-report.py reports a user FAIL — destination counts below the scan

baseline beyond tolerance.

Cause: Incomplete items (throttling truncation, transient errors), or a legitimate exclusion not

subtracted from the expected count.

Fix: First confirm the gap isn't an agreed exclusion (Recoverable Items, filtered date

range) — subtract those from expected. If it's real, re-run a Delta for that user, then   re-validate. Persistent per-item failures: review the run-log error rows and CloudM's   documented handling for those item types (verify for your version).

### Items delivered after cutover are missing

Symptom: Mail that arrived in M365 during the MX switch isn't in Google.

Cause: No post-cutover delta was run.

Fix: Always run a post-cutover `Delta Run – <Scope> – <Stage>` to sweep items delivered to

M365 during the switch. Make it a required step in the cutover runbook.

## Permissions & sharing

### Over-sharing / unexpected "anyone" links flagged

Symptom: validate-migration-report.py --check-permissions reports over-shared items.

Cause: Source sharing translated to broad Google sharing, or profile permission-mapping settings.

Fix: Correct the sharing on the affected items; review the profile's permission-handling options

and re-run a permission spot-check (verify CloudM permission-mapping behavior for your version).

### Shared Drive content lands in the wrong place or with wrong members

Symptom: SharePoint/team content in an unexpected Shared Drive or with wrong membership.

Cause: Incorrect file source→Shared Drive mapping in the user list.

Fix: Fix the mapping (regenerate with build-migration-userlist.py, review, re-import),

re-migrate the affected content, re-validate T4.

## Mail flow after cutover

### Mail not delivering to Gmail, or outbound failing SPF/DKIM/DMARC

Symptom: T5 fails — inbound not arriving or outbound authentication failing.

Cause: MX/DNS not fully switched, or SPF/DKIM/DMARC misaligned for Google.

Fix: Verify the domain's MX points to Google and that SPF, DKIM (Google-published

key), and DMARC are aligned. Treat DNS changes under change control. If a wave's mail flow can't   be made healthy, invoke the documented rollback (revert MX, keep M365 authoritative) and   re-cut in the next window.

## Destination accounts

### Users missing or suspended at migration time

Symptom: check-migration-health.py reports MISSING or INACTIVE destination accounts; per-user

writes fail.

Cause: Provisioning (GCDS/SCIM) lag, unlicensed, or suspended accounts.

Fix: Provision/license/unsuspend the affected accounts from the identity source of truth before

re-running the wave's delta. Re-run the health check to confirm HEALTHY before proceeding.

# Best Practices

Durable practices for executing M365→Google migrations with CloudM Migrate reliably at scale.

## Sequencing & waves

Always pilot first. Prove Migration Profile – Mail+Drive – Standard and both connections on

Migration Wave – Pilot – Wave0 before any production wave. Choose pilot users who span the hardest   data types (huge mailbox, large OneDrive, Shared-Drive/SharePoint heavy).

Pre-stage everything you can. Move the historical bulk of bytes days before the change window so

the cutover-window delta is small and fast. Cutover risk scales with how much data crosses during   the window — keep it minimal.

One profile, many waves. Reuse a single approved profile across waves so behavior is consistent

and predictable; change the profile only through review.

Cohort waves to departments/sites. Keeps communications, support, and rollback contained to a

known group.

Sequence waves under the throttling ceiling. Don't run so many concurrent pre-stage/delta passes

that you saturate Microsoft Graph or Gmail API quotas — use plan-migration-waves.py guidance.

## Throttling & throughput

Expect provider throttling, design for it. Microsoft (Graph/Exchange) and Google (Gmail/Drive)

both throttle; treat 429/backoff as normal signal, not failure. Tune concurrency down when throttled   rather than retrying blindly.

Scale self-hosted horizontally if throughput is the bottleneck — more migration servers/workers,

not just bigger ones (verify scaling model for your CloudM version).

Run pre-stage off-hours where provider quotas are less contended; reserve the change window for

the small final delta.

## Validation & data integrity

Reconcile against the Scan baseline, not against a guess. Capture per-user scan totals before

pre-stage and compare final counts to them.

Agree a variance tolerance up front and subtract known exclusions (Recoverable Items, filtered

date ranges) so the comparison is honest.

Always run a post-cutover delta. Items delivered to M365 during the MX switch must be swept.

Check permissions and over-sharing explicitly. Confirm migrated Drive/Shared-Drive sharing

matches intent and that no unintended "anyone" links were created.

## Change control & safety

Treat MX/DNS cutover as the highest-impact change. Stage it under change control with a written

runbook and a pre-agreed rollback (revert MX, M365 stays authoritative).

Keep the source read-only in effect until validated. Don't decommission M365 mailboxes/data

until the wave passes its validation gate — the source is your rollback.

Verify SPF/DKIM/DMARC before and after each cutover; misaligned auth silently damages

deliverability.

## Security & credentials

Never put secrets in code or the repo. Entra client secrets/certs and the Google service-account

JSON key live only in the CloudM platform's secured credential store / your secrets manager. The   included scripts use OAuth/ADC and read no secrets from source.

Least privilege on both sides. Grant only the Graph permissions and DWD scopes CloudM's

connectors require (verify the exact lists for your version); remove them after the project.

Rotate and revoke on completion. Retire the app registration secret, the service-account key,

and the DWD grant when the migration closes.

## Operations

Watch health between passes. Run check-migration-health.py to catch rising error/throttling

rates and destination license/account issues before they compound across waves.

Document per-wave outcomes. Keep each Validation Report – <Scope> – <Stage> as the audit

record of what moved and how it was verified.

Defer CloudM specifics to CloudM. For console behavior, licensing, fidelity matrices, and

version-specific features, use CloudM's own documentation and support — this playbook governs   procedure and sequencing, not the tool's internals.

# Deliverables Summary

Everything included in this solution, on one page.

## Documentation

| Document | What it covers |
| --- | --- |
| Solution Overview | The CloudM Migrate model (platform, connections, profiles, scan/pre-stage/delta), where it fits vs native + other tools, the wave approach, and the deployment model. |
| Requirements Guide | Solution-specific prerequisites R1–R7 (CloudM platform, M365 source app registration, Google service account + DWD, destination users/Shared Drives, user-list mapping, profile design, cutover/rollback) on top of the shared Google global requirements. |
| Implementation Guide | Exact ordered steps: Assess → Design → Configure → Pilot → Validate → Expand, with named artifacts, pass/fail gates, and rollback. CloudM console internals deferred to CloudM docs. |
| Testing & Validation | T1–T8 validation procedures with expected pass/fail, including item-count reconciliation, permissions, and mail-flow checks. |
| Troubleshooting | Common failure modes — throttling/API limits, app-consent/DWD permission errors, incomplete/delta items, mail-flow issues — with resolutions. |
| Best Practices | Durable practices for reliable sequencing, throttling, validation, change control, and credential hygiene. |
| Executive Summary | Crisp outcome/approach/why-low-risk summary for decision-makers. |

## Python tools (5)

All tools are safe-by-default (read-only or --dry-run unless --apply), use OAuth / ADC (no hardcoded credentials or keys), and target the Google Workspace Admin SDK / APIs (and read the Microsoft side only where noted). Requires Python 3.10+; where Google client libraries are used: pip install google-api-python-client google-auth.

| Script | What it does |
| --- | --- |
| assess-migration-readiness.py | Read-only discovery/assessment. Sizes the migration from the Google destination directory (user/license coverage) and a source inventory export (mailbox/OneDrive/SharePoint sizes), and flags gaps. Produces the assessment baseline. |
| build-migration-userlist.py | Builds the source→destination user-list CSV that CloudM consumes: reconciles a source user export against the Google directory, maps file sources to Shared Drives. Dry-run by default; --apply writes the CSV. Headers align to CloudM's import template (verify for your version). |
| plan-migration-waves.py | Wave planner + throttling guidance. Groups users into sequenced waves (pilot first), orders pre-stage/delta passes, and computes concurrency guidance to stay under Microsoft Graph / Google API throttling ceilings. Read-only planning output. |
| validate-migration-report.py | Post-migration validation report generator. Compares destination Gmail/Drive item counts against the scan baseline per user, spot-checks Drive/Shared-Drive permissions (--check-permissions), and reports pass/fail per the agreed tolerance. Read-only. |
| check-migration-health.py | Policy/health/throttling check. Between passes, watches destination account/license health and surfaces throttling/error signals so drift is caught before it compounds across waves. Read-only. |

## Packaging

CLOUDM-Solution.pdf — compiled solution document (all sections above).

CLOUDM-Scripts.zip — the five Python tools.

# Appendix A — PowerShell Scripts

The following scripts are included in the accompanying ZIP. Each script's own header documents its full usage and expected results.

## assess-migration-readiness.py

## build-migration-userlist.py

## check-migration-health.py

## plan-migration-waves.py

## validate-migration-report.py