Google Workspace Migrate — Deployment & Large-Scale Migration Execution

Implementation Solution Guide

Version 1.0.0    ·    2026-07-06

# Contents

Right-click and choose “Update Field” to build the table of contents.

# Executive Summary

Outcome. The organization can move enterprise-scale files and mail from Microsoft 365 (SharePoint Online, OneDrive, Exchange Online) into Google Workspace (Drive, Shared Drives, Gmail) using Google Workspace Migrate, Google's own large-scale migration platform — deployed, mapped, throttled, waved, and validated so large volumes move reliably and with preserved ownership and sharing.

Approach. This is a tool deployment-and-execution playbook. It stands up the self-hosted node platform (management/database node plus scalable worker nodes), wires the Microsoft 365 and Google connections, builds mappings and the identity bridge, and runs data in throttled waves using the house model Assess → Design → Configure → Pilot → Validate → Expand. A small named pilot wave is migrated end to end — pre-stage bulk pass, delta pass, then gated cutover — and validated for item-count, permission, and mail parity before any production wave runs. Five Python tools (Google Workspace Admin SDK and Microsoft Graph) handle the scriptable edges: node sizing from a real source baseline, mapping/connection artifact generation, wave batching with a throttling plan, live migration health/throttling monitoring, and post-migration validation reporting. Every tool is safe-by-default (read-only or dry-run until explicitly applied) with no credentials in code; the tool's deep console internals are deferred to Google's own documentation and version-specific behavior is flagged "verify for your version."

Why it is low-risk. Nothing scales until a pilot passes explicit pass/fail gates. The bulk of the data moves while users keep working on the source; only cutover is high-impact, and it runs inside a change window with a tested, reversible rollback (routing reverts, source data is preserved). Throttling is planned conservatively and calibrated from measured pilot throughput, so migrations run steadily under source/target API limits rather than tripping them. The result is a predictable, auditable, enterprise-scale migration on Google's native tool — for a fraction of the cost of an open-ended consulting engagement.

# Solution Overview

## What this is

This solution is the deployment and large-scale execution playbook for Google Workspace Migrate (GWSMigrate) — Google's own on-premises platform for moving enterprise volumes of files and mail from Microsoft 365 (SharePoint Online, OneDrive for Business, Exchange Online) into Google Workspace (Drive, Shared Drives, Gmail). It covers everything an enterprise migration team must own to run the tool at scale: designing and sizing the node/database platform, wiring the Microsoft 365 and Google connections, building mappings and bridges, sequencing throttled migration waves, and validating the results.

It is a tool playbook, not a strategy paper. It gives you the architecture, prerequisites, setup order, mapping and wave design, throttling levers, and validation gates you need to run Google Workspace Migrate to implement. Because the tool's console changes across releases, the deep console internals, exact screen labels, licensing, and support boundaries are deferred to Google's own Google Workspace Migrate documentation — where a step depends on version-specific behavior it is flagged "verify for your version." The *procedure, sequencing, and design* are given here; the *button-by-button console detail* you confirm against Google's current docs.

### Where it sits among the migration solutions

The tool-agnostic program/strategy playbook owns the *decision* of how to migrate (waves,

coexistence, cutover strategy, org change) independent of tool choice. This solution assumes that   decision is made and executes it on Google's native tool.

The third-party tool playbooks (BitTitan MigrationWiz, CloudM Migrate, and the Google

Workspace Migration for Microsoft Exchange / GWMME desktop tool) cover *those* tools. This   solution is specifically for Google Workspace Migrate, the server-based platform Google   provides for large-scale file and mail moves.

Use Google Workspace Migrate when the dataset is large enough (typically SharePoint/OneDrive at

scale plus mail) to justify standing up node infrastructure and running parallelized, throttled   waves under central control.

## How it works (reference architecture)

Google Workspace Migrate is a self-hosted platform the organization runs on Windows Server hosts inside its own network. Its logical parts:

Platform node (management node) — runs the management service, the web console the migration

team drives, and the encrypted platform database that holds project state, mappings, scan   results, and run history. Named here GWSM Platform Node – Migration – Prod.

Worker (data) nodes — the horsepower. Each worker node runs the scan and transfer work in

parallel; you add nodes to increase throughput. Named GWSM Worker Node – Migration – NN   (e.g. 01, 02).

Connections — credentialed links to each side: a Microsoft 365 connection (app

registration in Microsoft Entra ID with Graph/SharePoint scopes) named   Connection – Microsoft 365 – Source, and a Google connection (a Google Cloud project + a   service account with domain-wide delegation) named Connection – Google Workspace – Target.

Mappings — how a source object maps to a target object: user → user, OneDrive → My Drive,

SharePoint site/library → Shared Drive, mailbox → Gmail. Built from a mapping CSV the team   authors and imports. Named per scope, e.g. Mapping – Finance OneDrive – Pilot.

Bridges — the connective identity mapping that resolves **source identities to target

identities** (and permissions) so ownership and sharing survive the move. Named   Bridge – Identity – Corp.

Scans then migrations — you scan first (read-only discovery of what exists and how big),

review the scan, then run a migration for a defined scope. Every run is a wave.

The team drives all of this from the platform node's console; the Python tools in this solution work *alongside* it against the Google Workspace Admin SDK and Microsoft Graph to size nodes, generate the mapping/connection artifacts the tool consumes, plan throttled waves, and validate the target after each wave — the parts that are scriptable outside the tool's own console.

### The wave model

Data moves in waves — a scoped batch (a set of users/sites) migrated together:

Pre-stage (bulk) pass — the large, slow copy of the bulk of the data while users still work

on the source. Run with conservative throttling over days/nights.

Delta pass(es) — incremental re-runs that carry only what changed since the last pass.

Cutover — the final delta plus the switch of the user to the target (mail routing / user

communication). High-impact; gated and reversible.

Waves are named Migration Wave – <Scope> – <Stage> (e.g. Migration Wave – Finance – Pilot, Migration Wave – Sales – Delta).

## Deployment model

This solution follows the house model end to end, with explicit pass/fail gates and a documented rollback for every production change:

Assess → Design → Configure → Pilot → Validate → Expand.

Assess — inventory the source (item counts, data volume, largest mailboxes/sites, sharing

complexity); size the node platform; confirm prerequisites.

Design — node count/sizing, connection scopes, mapping strategy (OneDrive→My Drive,

SharePoint→Shared Drive), identity bridge, wave plan and throttling budget.

Configure — stand up nodes + database, create both connections, import mappings and the

identity bridge, run a scan.

Pilot — migrate a small named wave (Migration Wave – Finance – Pilot) pre-stage → delta →

cutover, measuring throughput, error rate, and throttling behavior.

Validate — item-count parity, permission/ownership fidelity, and (for mail) message-count and

mail-flow checks against pass/fail gates.

Expand — schedule production waves only after the pilot passes, tuning throttling and node

count from the pilot's measured throughput.

## Benefits

Google's native large-scale tool, run correctly: node platform sized to the dataset, waves

parallelized and throttled so you don't trip source or target API limits.

Predictable, reversible rollout — pilot-first with measured throughput and defined gates

before any production wave; cutover is the only high-impact step and it is gated and reversible.

Fidelity preserved — identity bridge and mapping design keep ownership and sharing intact;

post-wave validation proves item-count and permission parity rather than assuming it.

Scriptable edges — the five Python tools remove the manual, error-prone parts (sizing,

artifact generation, throttling math, validation) while leaving the tool's console authoritative.

## Limitations / scope boundary

Tool-console internals are deferred to Google's documentation. Exact console labels, wizard

screens, node installer prompts, supported source/target scopes, and licensing/support terms   change across releases — this playbook gives procedure and sequencing and flags version-specific   behavior "verify for your version." Always confirm the current supported-scope matrix (what   content types Migrate does and does not carry) in Google's docs before committing a wave plan.

Not a Teams/Chat data-mover. This solution scopes files (SharePoint/OneDrive) and mail,

the workloads Google Workspace Migrate is built for. Teams/Chat history and other workloads are   out of scope here and follow their own approach.

Gemini or any preview target-side feature referenced is flagged "verify in your tenant."

The Python tools are safe-by-default (read-only or --dry-run until --apply) and never

drive an invented tool API — they generate the CSV/JSON artifacts Migrate consumes or read the   Admin SDK / Graph to validate; they do not fabricate a private Migrate endpoint.

# Requirements

These are the solution-specific prerequisites for deploying and running Google Workspace Migrate at scale. They build on the shared Global Requirements — Google Workspace & Gemini Solutions (global-requirements-google.md): a provisioned Google Workspace / Cloud Identity tenant with super-admin (GR-1), administrative access to the source Microsoft 365 / Entra environment (GR-2), DNS control for routed domains (GR-3), an identity source of truth and provisioning model (GR-4), a pilot OU/group and change control (GR-5), and engagement with security/compliance stakeholders (GR-6). Do not re-verify those here; confirm them, then verify the items below.

Where a requirement depends on Google Workspace Migrate's current release (supported node OS, supported source/target scope, sizing guidance), verify against Google's Google Workspace Migrate documentation for your version — those specifics change and are not restated here.

__________________________________________________

## R1. Node platform infrastructure (Windows Server hosts + database)

Description: Windows Server hosts to run the platform node (management service + web

console + platform database) and one or more worker nodes, each meeting Google Workspace   Migrate's current CPU/RAM/disk and supported-OS requirements, inside the organization's network.

Why required: Google Workspace Migrate is self-hosted; scan/transfer throughput is a direct

function of node count and node sizing. Under-provisioning is the most common cause of missed   migration timelines.

How to verify: Confirm the provisioned hosts meet Google's current minimum spec (verify

for your version) and that the platform node's database volume has headroom for project state and   scan results across all planned waves. Run node-sizing-assessment.py (this solution) against the   source inventory to get a recommended node count for the target throughput.

How to implement if missing: Provision the hosts (physical or IaaS), install the supported OS,

and reserve a dedicated encrypted volume for the platform database. Size to the recommendation   from node-sizing-assessment.py, rounding up for delta passes and headroom.

## R2. Microsoft 365 source app registration + scopes (`Connection – Microsoft 365 – Source`)

Description: An Entra ID app registration with the Microsoft Graph / SharePoint

application permissions Google Workspace Migrate requires to read Exchange Online, OneDrive, and   SharePoint at scale, plus admin consent granted tenant-wide.

Why required: The Microsoft 365 connection authenticates as this app to scan and read source

content; missing or unconsented scopes are the top cause of scan/transfer permission failures.

How to verify: In the Entra admin center, confirm the app registration exists, the required

application permissions are present, and admin consent is granted (green status). Confirm the   client secret/certificate is current and stored in a secret manager, not in code.

How to implement if missing: Register the app, add the permissions Google Workspace Migrate's

documentation specifies for your version, grant admin consent, and record the client ID +   secret reference for the connection. Use least privilege the tool supports.

## R3. Google target Cloud project + delegated service account (`Connection – Google Workspace – Target`)

Description: A Google Cloud project with the required Workspace APIs enabled (Admin SDK

Directory, Drive, Gmail, Groups) and a service account with domain-wide delegation authorized   for the scopes Migrate uses to write into Drive/Shared Drives and Gmail.

Why required: The Google connection impersonates target users via the delegated service

account to create content and set ownership/permissions on the target side.

How to verify: In the Google Admin console under **Security → Access and data control → API

controls → Domain-wide delegation**, confirm the service account's client ID is present with the   exact OAuth scopes required. Confirm the APIs are enabled in the Cloud project.

How to implement if missing: Create the Cloud project, enable the APIs, create the service

account, and authorize its client ID for the required scopes in Domain-wide delegation. Store the   key in a secret manager; never commit the key.

## R4. Network path, bandwidth, and firewall egress

Description: Reliable, sized network egress from the node platform to both Microsoft 365

and Google endpoints, with any required firewall/proxy allow-listing, and enough sustained   bandwidth to move the assessed data volume within the migration window.

Why required: Every byte transits the nodes; bandwidth and firewall egress cap real

throughput regardless of node count.

How to verify: Confirm the platform/worker nodes can reach the Microsoft and Google service

endpoints (verify the current endpoint/URL list for your version) through the corporate   proxy/firewall. Compare available sustained bandwidth against the assessed volume ÷ window.

How to implement if missing: Allow-list the required egress, provision bandwidth (or place

nodes where bandwidth is best), and schedule bulk pre-stage passes for off-peak windows.

## R5. Source inventory / discovery baseline

Description: A quantified inventory of the source: user/mailbox counts and sizes,

OneDrive/SharePoint site and library counts, item counts, largest objects, and sharing/permission   complexity — the baseline every wave is validated against.

Why required: Node sizing, wave scoping, throttling budgets, and validation gates all key off

real numbers. Without a baseline you cannot prove parity after a wave.

How to verify: Run node-sizing-assessment.py (reads Microsoft Graph, read-only) to produce

the inventory and volume/throughput estimate; sanity-check against the Microsoft admin center   reports.

How to implement if missing: Grant the assessment app read scopes and run the discovery before

designing waves; store the baseline as the validation reference.

## R6. Mapping and identity-bridge source data (`Mapping – … `, `Bridge – Identity – Corp`)

Description: Authoritative source→target mapping data (which source user/site maps to which

target user/Shared Drive) and the identity bridge data that resolves source identities to   target identities so ownership/sharing survive.

Why required: Mappings and the bridge are what Google Workspace Migrate consumes to route

content and preserve permissions; wrong or incomplete mappings misplace data or drop sharing.

How to verify: Run connection-mapping-generator.py --dry-run (this solution) to produce and

validate the mapping CSV + bridge from the directory data; confirm every in-scope source object   resolves to exactly one target.

How to implement if missing: Reconcile the directories (see GR-4 source of truth), then

generate the mapping/bridge artifacts and review before import.

## R7. Migration service accounts and least-privilege operations

Description: Dedicated, named service identities for the migration platform (the M365 app, the

Google delegated service account) with least privilege, plus a defined change window for   cutover waves (mail routing changes are high-impact — GR-3/GR-5).

Why required: Migration runs with powerful cross-tenant access; scoping it to dedicated,

auditable identities and gating cutover under change control limits blast radius.

How to verify: Confirm the identities are dedicated (not a person's admin account), documented,

and revocable; confirm a change/approval path exists for cutover.

How to implement if missing: Create the dedicated identities, document them, and agree the

cutover change window and rollback with the owners before scheduling production waves.

# Global Requirements — Google Workspace & Gemini Solutions

These requirements apply to every solution in the Google category. They are the common foundation each Google Workspace / Gemini solution assumes is already in place (or stands up as part of its own Requirements section). Verify each before starting a solution's implementation steps.

Vendor boundary (applies to every Google solution). The Google Admin console (admin.google.com), Google Cloud / Cloud Identity, and the Microsoft / Entra sides are authored at exact, current click-by-click detail from the vendors' public documentation. Gemini Enterprise capabilities that are in preview or rolling out are cited or flagged "verify in your tenant" — never invented. Third-party migration tools (e.g. for mail/Drive/Chat data movement) and third-party enterprise apps (ServiceNow, SAP, Databricks, etc.) are integrated at the pattern/architectural level; their internal console steps are deferred to the vendor's own docs.

## 1. Google Workspace / Cloud Identity tenant

Description: A provisioned Google Workspace (or Cloud Identity) tenant with a super-admin

account for configuration, and the appropriate Workspace edition/licensing for the capability in   scope (e.g. Enterprise Plus for Vault/CAA/DLP, Gemini/AI add-on where required).

Why required: All configuration, policy, and API work is performed against this tenant.

How to verify: Sign in to admin.google.com as a super-admin; confirm edition and license

counts under Billing / Subscriptions.

How to implement if missing: Provision the tenant and licenses through Google or an authorized

reseller before starting.

## 2. Source Microsoft 365 / Entra environment (for migration & coexistence)

Description: For migration/coexistence/identity solutions, administrative access to the source

Microsoft 365 tenant and Microsoft Entra ID (Global Administrator or the least-privilege   roles the solution names).

Why required: Migration, directory sync, SSO federation, and coexistence read from and change

the Microsoft side.

How to verify: Confirm access to the M365 admin center and the Entra admin center with the

required role.

How to implement if missing: Obtain the role from the M365/Entra tenant owner.

## 3. DNS control for the routed domains

Description: Ability to create/modify DNS records (MX, SPF, DKIM, DMARC, TXT, CNAME) for the

domains being migrated, coexisting, or verified.

Why required: Domain verification, mail routing/coexistence, and authentication all depend on

DNS changes.

How to verify: Confirm access to the authoritative DNS zone for each domain.

How to implement if missing: Coordinate with whoever controls DNS; stage changes under change

control (mail-flow changes are high-impact).

## 4. Identity & provisioning source of truth

Description: A defined identity source of truth (on-prem AD, Entra ID, or an HR/IGA system)

and the sync mechanism (e.g. Google Cloud Directory Sync (GCDS) or SCIM-based provisioning).

Why required: Consistent users/groups across ecosystems underpin SSO, licensing, and access.

How to verify: Confirm which directory is authoritative and how objects flow into Google.

How to implement if missing: Define the source of truth and provisioning model before configuring

SSO or migrating.

## 5. A pilot scope (OU / group) and change control

Description: A pilot organizational unit or group to validate on before fleet-wide rollout,

and a change-control process for production changes (especially mail flow, DNS, identity, and DLP).

Why required: Every solution follows an Assess → Configure → Pilot → Validate → Expand model;

the pilot proves the design and change control protects production.

How to verify: Confirm a named pilot OU/group exists and a change window/approval path is available.

How to implement if missing: Create a pilot OU/group and agree the change-control process with the

owners before making production changes.

## 6. Security, compliance & governance stakeholders

Description: Engagement with the security (CISO), legal/eDiscovery, and data-governance

stakeholders whose policies the configuration must satisfy (DLP, retention, Vault/Purview, and any   regulatory regime such as ITAR/DFARS/Assured Controls where applicable).

Why required: Data governance, eDiscovery, DLP, and regulated-workload settings must align to

enterprise policy and legal requirements, not just technical defaults.

How to verify: Confirm the applicable policies and named stakeholders/approvers.

How to implement if missing: Identify the owners and obtain the policy/compliance requirements

before configuring governance controls.

*The deployment model across every Google solution is the same: Assess → Configure → Pilot → Validate → Expand, with explicit pass/fail gates and a documented rollback for production changes.*

# Implementation

Run these steps in order. They follow the house model Assess → Design → Configure → Pilot → Validate → Expand, pilot-first, with explicit pass/fail gates and a documented rollback for every production change. Every artifact is named with the convention <Purpose> – <Scope> – <Stage>; reuse the exact names in testing, troubleshooting, and the scripts.

Tool-console boundary. Where a step drives Google Workspace Migrate's own console (node installer prompts, connection wizard, scan/migration screens), the procedure and sequence are given here but the exact screen labels and version-specific options are deferred to Google's Google Workspace Migrate documentation — confirm them for your version as you go. The Python tools operate outside the console against the Admin SDK / Graph and generate the artifacts the console imports.

__________________________________________________

## Phase 1 — Assess

### 1.1 Baseline the source (read-only)

Run the discovery to quantify the migration and feed sizing:

python node-sizing-assessment.py --graph --out baseline-source.json

This reads Microsoft Graph (read-only) for mailbox/OneDrive/SharePoint counts, sizes, largest objects, and sharing complexity, and prints a recommended worker-node count for a target throughput and window. Store the output as baseline-source.json — it is the reference every validation gate compares against.

### 1.2 Confirm prerequisites

Verify R1–R7 (Requirements) and the shared GR-1…GR-6. Do not proceed until the node hosts (R1), both connection identities (R2/R3), network egress (R4), and the pilot scope (GR-5) are confirmed.

Gate A (enter Design): baseline captured; node hosts provisioned; both connection identities created and consented; pilot OU/group named.

__________________________________________________

## Phase 2 — Design

### 2.1 Size the platform

Using baseline-source.json, fix the node platform:

GWSM Platform Node – Migration – Prod — one management/database node (verify current spec).

GWSM Worker Node – Migration – NN — worker nodes at the count node-sizing-assessment.py

recommends for the throughput needed to finish within the window (round up for delta passes).

### 2.2 Design mappings and the identity bridge

Decide the target shape and generate the artifacts (dry-run):

python connection-mapping-generator.py --dry-run \
    --graph --directory --out mapping-plan/

Standard mapping design:

OneDrive → My Drive per user (Mapping – <Dept> OneDrive – <Stage>).

SharePoint site/library → Shared Drive (Mapping – <Site> SharePoint – <Stage>).

Mailbox → Gmail per user (Mapping – <Dept> Mail – <Stage>).

Bridge – Identity – Corp — resolves every source identity to a target identity so ownership

and sharing survive. Every in-scope source object must resolve to exactly one target.

### 2.3 Plan waves and the throttling budget

Group in-scope users/sites into waves and compute a safe throttling budget:

python wave-batch-builder.py --dry-run \
    --baseline baseline-source.json --wave-size 250 --out waves/

This emits per-wave batch files (Migration Wave – <Scope> – <Stage>) and a throttling plan (concurrency per node, requests/sec ceilings) sized to stay under source/target API limits. Start conservative; the pilot will calibrate the real ceiling.

Gate B (enter Configure): node count fixed; mappings + Bridge – Identity – Corp generated and reviewed (every object resolves once); wave plan + throttling budget drafted.

__________________________________________________

## Phase 3 — Configure

### 3.1 Stand up the node platform

Install Google Workspace Migrate on GWSM Platform Node – Migration – Prod (follow Google's

node installer for your version — screen labels deferred to Google's docs). Point it at the    dedicated encrypted database volume (R1).

Install and register each GWSM Worker Node – Migration – NN to the platform node.

Confirm all nodes report healthy in the console before creating connections.

### 3.2 Create the connections

Connection – Microsoft 365 – Source — enter the Entra app registration (R2) client ID +

secret reference and the scopes; test the connection until it authenticates.

Connection – Google Workspace – Target — enter the Google delegated service account (R3);

test until it authenticates and can impersonate a target user.

Validate connection health before importing anything:

python migration-health-check.py --connections --dry-run

### 3.3 Import mappings and the bridge

Import the reviewed mapping-plan/ CSVs and Bridge – Identity – Corp into the project (console import — verify the import screen for your version). Re-run the generator with --validate to confirm the imported set matches what was generated.

### 3.4 Run a scan (read-only discovery)

Run a scan over the pilot scope only. A scan is read-only: it discovers what exists and how big, with no writes to the target. Review the scan for unsupported items, oversized objects, and permission anomalies before any migration.

Gate C (enter Pilot): all nodes healthy; both connections test-pass; mappings + bridge imported and validated; pilot scan complete and reviewed with no blocking anomalies.

__________________________________________________

## Phase 4 — Pilot (pilot-first, on `Migration Wave – Finance – Pilot`)

Run the pilot wave through the full pre-stage → delta → cutover sequence on the named pilot scope (GR-5). Rollback for each step is defined below.

### 4.1 Pre-stage (bulk) pass

Start the migration for Migration Wave – Finance – Pilot with the throttling plan from Phase 2. Users keep working on the source; nothing is cut over. Monitor throughput and error rate:

python migration-health-check.py --wave "Migration Wave - Finance - Pilot" --watch

Rollback (pre-stage): the source is untouched and the target is not yet live to users — pause or stop the run, delete the partially-migrated target content for the wave, correct the mapping or throttling, and re-run. No user impact.

### 4.2 Delta pass

Re-run the wave in delta mode to carry only what changed since the pre-stage pass. Confirm the delta completes cleanly and the incremental item count is small and expected.

### 4.3 Cutover (high-impact — gated)

Only inside the agreed change window (R7/GR-5):

Run the final delta.

Switch the pilot users to the target per the routing/communication plan (mail routing is the

high-impact change — coordinate DNS/routing under change control, GR-3).

Rollback (cutover): if validation (Phase 5) fails, revert mail routing to the source under the same change window, keep users on the source, and treat the migrated target content as staging until re-validated. Because routing is reversible and the source data is preserved through cutover, the wave can be re-run.

Gate D (Pilot passes → enter Validate/Expand): pre-stage + delta + cutover completed for the pilot wave; error rate within threshold; throttling stable (no sustained source/target throttling).

__________________________________________________

## Phase 5 — Validate

Validate the pilot against the baseline before scaling. Run the post-migration validation report:

python post-migration-validation.py \
    --wave "Migration Wave - Finance - Pilot" \
    --baseline baseline-source.json --out validate-pilot/

It compares target item counts vs. source baseline, checks ownership/permission fidelity (sharing preserved via Bridge – Identity – Corp), and, for mail, checks message-count parity and basic mail-flow. See 05-testing.md for the pass/fail criteria of each gate.

Gate E (enter Expand): item-count parity within threshold; permissions/ownership preserved; mail count + flow pass. Any gate failure → do not expand; fix and re-validate.

__________________________________________________

## Phase 6 — Expand

Only after the pilot passes Gate E:

Tune node count and the throttling plan using the pilot's measured throughput

(wave-batch-builder.py --calibrate --from validate-pilot/).

Schedule production waves (Migration Wave – Sales – Prod, etc.) in dependency order, each with

the same pre-stage → delta → cutover sequence, gates, and rollback.

Validate every production wave with post-migration-validation.py before closing it; keep

migration-health-check.py --watch running through each wave to catch throttling early.

Decommission node infrastructure and revoke the migration service identities (R7) only after the

final wave is validated and closed.

# Testing & Validation

Each test below has an explicit pass/fail result. Run them at the gate indicated in 03-implementation.md. The named artifacts (Migration Wave – Finance – Pilot, Bridge – Identity – Corp, the connections) are the same ones created during implementation.

__________________________________________________

## T1. Node platform health (Gate C)

Procedure: In the Google Workspace Migrate console, confirm `GWSM Platform Node – Migration –

Prod and every GWSM Worker Node – Migration – NN` report healthy and connected. Confirm the   platform database volume has headroom.

Pass: all nodes healthy/connected; database volume < agreed utilization threshold.

Fail: any node unhealthy/disconnected, or database volume near capacity → resolve before

scanning.

## T2. Connection authentication (Gate C)

Procedure: Run python migration-health-check.py --connections --dry-run, then use the

console's built-in connection test for Connection – Microsoft 365 – Source and   Connection – Google Workspace – Target.

Pass: both connections authenticate; the Google connection can impersonate a target user; no

scope/consent errors.

Fail: auth or scope error → fix the app registration (R2) or domain-wide delegation (R3) and

retest.

## T3. Mapping & bridge integrity (Gate C)

Procedure: Run python connection-mapping-generator.py --validate --against mapping-plan/.

Pass: every in-scope source object resolves to exactly one target; Bridge – Identity – Corp

resolves all source identities; no duplicates or orphans.

Fail: any unresolved, duplicate, or orphaned mapping → correct the source data and regenerate

before importing.

## T4. Pilot scan review (Gate C)

Procedure: Review the pilot scan output for unsupported item types, oversized objects, and

permission anomalies.

Pass: no blocking unsupported items; oversized objects identified and dispositioned; anomalies

understood.

Fail: blocking unsupported/oversized items unaddressed → disposition them (or confirm expected

behavior for your version in Google's docs) before migrating.

## T5. Pre-stage throughput & throttling (Gate D)

Procedure: During the pilot pre-stage pass, run `python migration-health-check.py --wave

"Migration Wave - Finance - Pilot" --watch`.

Pass: sustained throughput within the planned range; no sustained source/target throttling

(429/Graph throttling or Google rate-limit responses stay within the plan's ceiling); error rate   below threshold.

Fail: sustained throttling or error rate above threshold → lower concurrency in the throttling

plan and re-run (see 06-troubleshooting.md).

## T6. Delta correctness (Gate D)

Procedure: After the delta pass, confirm the incremental item count is small and equals the

changes made on the source since pre-stage.

Pass: delta carries only changed items; no full re-copy; no unexpected deletions on target.

Fail: delta re-copies everything or misses changes → verify delta configuration for your

version in Google's docs and re-run.

## T7. Item-count parity (Gate E)

Procedure: Run `python post-migration-validation.py --wave "Migration Wave - Finance - Pilot"

--baseline baseline-source.json --out validate-pilot/`.

Pass: target item counts (Drive files, Shared Drive contents) match the source baseline within

the agreed threshold (accounting for documented unsupported items).

Fail: counts diverge beyond threshold → investigate the delta of missing items in the report

and re-run the affected scope.

## T8. Permission & ownership fidelity (Gate E)

Procedure: From the same validation report, review the ownership/permission comparison

(sharing preserved via Bridge – Identity – Corp).

Pass: owners and sharing on target match the intended source-to-target mapping; no

over-permissioning (no unexpected public/broad sharing introduced).

Fail: ownership wrong or sharing dropped/broadened → fix the bridge/mapping and re-run for the

affected objects.

## T9. Mail count & flow parity (Gate E, mail waves)

Procedure: From the validation report, compare per-mailbox message counts source vs. target

and send a round-trip test to a cutover pilot user.

Pass: message counts match within threshold; test mail delivers to the target mailbox; no

routing loop.

Fail: count mismatch or delivery failure → verify mail mapping/routing and re-run the mail

scope; for routing issues revert routing (cutover rollback) and diagnose.

## T10. End-to-end pilot sign-off (Gate D→E)

Procedure: Confirm T1–T9 all pass for Migration Wave – Finance – Pilot.

Pass: all gates green → proceed to Expand and schedule production waves.

Fail: any gate red → do not expand; remediate and re-validate the affected test.

# Troubleshooting

Common failure modes running Google Workspace Migrate at scale, and how to resolve them. Named artifacts (Connection – Microsoft 365 – Source, Bridge – Identity – Corp, Migration Wave – Finance – Pilot, the throttling plan) are the ones created in 03-implementation.md.

For anything tied to a specific console screen, node installer prompt, or supported-scope behavior, verify against Google's Google Workspace Migrate documentation for your version — the resolutions below are procedural, not version-locked.

__________________________________________________

## Throttling / API rate limits

Symptom: throughput drops; logs show Microsoft Graph 429 / "throttled" or Google rate-limit / quota responses; migration-health-check.py --watch reports sustained throttle events (≥ threshold).

Cause: concurrency/request rate is above the source or target ceiling for your tenant.

Resolve: lower concurrency_per_node and the graph_rps_ceiling / google_rps_ceiling in the

throttling plan (wave-batch-builder.py), let the current run drain, and re-run. Prefer running   steadily under the ceiling over tripping throttling and backing off. Move heavy pre-stage   passes to off-peak windows. Re-raise ceilings only via --calibrate after a clean pilot.

## Connection authentication / permission errors

Symptom: Connection – Microsoft 365 – Source or Connection – Google Workspace – Target fails its test; scan or transfer aborts with auth/scope/consent errors.

Microsoft side: the Entra app registration (R2) is missing a required Graph/SharePoint

application permission or admin consent was not granted, or the client secret expired. Re-check   the permissions for your version, grant admin consent, rotate the secret in the secret manager.

Google side: the service account's client ID is not authorized in Domain-wide delegation for

the exact OAuth scopes (R3), a required API is not enabled in the Cloud project, or the service   account cannot impersonate the target user. Add the scopes in Admin console → Security → API   controls → Domain-wide delegation; enable the APIs. Confirm with   migration-health-check.py --connections.

## Mapping / identity-bridge errors

Symptom: content lands in the wrong target, ownership is wrong, or scan reports unresolved objects.

Cause: a source object doesn't resolve to exactly one target, or Bridge – Identity – Corp

is missing/duplicated identities.

Resolve: run connection-mapping-generator.py --validate — it flags unresolved, duplicate, or

orphaned identities. Fix the directory source of truth (GR-4), regenerate, review, and re-import.   Never migrate on an unvalidated mapping set.

## Delta pass re-copies everything, or misses changes

Symptom: the delta wave transfers far more (or far fewer) items than the changes made on the source since pre-stage.

Cause: delta/change-detection configuration or timing is off for your version.

Resolve: confirm the delta configuration and change-detection behavior in Google's docs **for

your version**; ensure the pre-stage pass fully completed before the delta; re-run the delta for the   affected scope. Use post-migration-validation.py to confirm the incremental count is expected.

## Incomplete / skipped / unsupported items

Symptom: validation shows an item-count shortfall beyond the parity threshold; scan/run logs list skipped or unsupported items.

Cause: items of a type/attribute Google Workspace Migrate does not carry, oversized objects, or

items that errored mid-transfer.

Resolve: open the validation report from post-migration-validation.py, identify the specific

missing items, and disposition them: re-run the failed items, handle oversized objects per Google's   supported-scope guidance for your version, and record documented unsupported types so the parity   threshold accounts for them. Do not close the wave until the shortfall is explained.

## Node platform / database issues

Symptom: a worker node shows unhealthy/disconnected; throughput collapses; console errors on the platform node.

Cause: node resource exhaustion (CPU/RAM/disk), the platform database volume near capacity,

or a node lost connectivity to the platform node.

Resolve: check node health in the console; free/expand the database volume (R1); restart the

affected GWSM Worker Node – Migration – NN and confirm it re-registers to   GWSM Platform Node – Migration – Prod. If throughput is structurally short of plan, add worker   nodes per node-sizing-assessment.py.

## Bandwidth / network egress bottleneck

Symptom: throughput is flat well below the plan even with nodes healthy and no throttling.

Cause: the corporate egress bandwidth or a proxy/firewall path is the cap (R4).

Resolve: confirm firewall/proxy allow-listing for the current endpoint list, measure available

sustained bandwidth vs. volume ÷ window, schedule bulk passes off-peak, or relocate nodes closer to   better egress. Node count cannot exceed what bandwidth allows.

## Mail routing / cutover problems

Symptom: after cutover, mail loops, bounces, or does not deliver to the target mailbox; the mail round-trip test (T9) fails.

Cause: mail routing/DNS not switched correctly, or coexistence routing conflict during cutover.

Resolve: this is the high-impact step — execute the cutover rollback: revert mail routing to

the source under the same change window (GR-3/R7), keep users on the source, and diagnose the   routing/DNS change before re-attempting. Source data is preserved through cutover, so the wave can   be re-run once routing is corrected.

## Permissions/sharing dropped or over-broadened on target

Symptom: validation (T8) shows ownership wrong, sharing lost, or unexpected public/broad sharing introduced.

Cause: bridge/mapping resolved identities incorrectly, or a source sharing construct mapped to a

broader target scope.

Resolve: correct Bridge – Identity – Corp/the mapping for the affected objects and re-run that

scope; treat any unexpected public sharing as a fail and remediate before closing the wave.

# Best Practices

Durable practices for deploying and running Google Workspace Migrate at scale. They complement the ordered steps in 03-implementation.md.

## Platform & sizing

Size from measured data, not guesses. Drive node count from the node-sizing-assessment.py

baseline (volume ÷ window ÷ per-node throughput), and round up for delta passes and headroom.   Under-provisioning silently blows the timeline.

Isolate the platform database. Put it on a dedicated, encrypted volume with backup; it holds

all project state, mappings, and scan results — losing it means re-scanning everything.

Confirm supported scope for your version first. Before committing a wave plan, verify in

Google's Google Workspace Migrate docs exactly which content types/attributes the tool carries and   which it does not — design mappings around the documented boundary, don't discover it mid-wave.

## Connections & identity

Least privilege, dedicated identities. Use a dedicated Entra app (`Connection – Microsoft 365

– Source) and a dedicated Google service account (Connection – Google Workspace – Target`) — not   a person's admin account — with only the scopes the current version requires. Store secrets in a   secret manager; never put keys in code, CSVs, or the repo.

Get the identity bridge right before scaling. Bridge – Identity – Corp is what preserves

ownership and sharing. Validate that every source identity resolves to exactly one target   (connection-mapping-generator.py --validate) before the pilot, not after.

## Waves, throttling & sequencing

Pilot first, always. Prove the full pre-stage → delta → cutover sequence on

Migration Wave – Finance – Pilot and pass every gate before any production wave.

Pre-stage bulk, delta close, cutover last. Move the bulk while users work on the source, carry

changes with deltas, and keep cutover (the only high-impact step) inside a change window with a   tested rollback.

Start throttling conservative, calibrate from the pilot. Begin below the API ceilings; use the

pilot's measured throughput (wave-batch-builder.py --calibrate) to raise concurrency safely. It   is faster to run steadily under the limit than to trip throttling and back off repeatedly.

Schedule bulk passes off-peak. Bandwidth is a hard cap; run the heavy pre-stage passes in

off-peak windows and keep cutover deltas small.

## Validation & change control

Validate every wave, not just the pilot. Run post-migration-validation.py and clear

item-count, permission, and mail gates before closing any wave. "It looked done" is not parity.

Watch throttling live. Keep migration-health-check.py --watch running through each wave so

sustained throttling is caught and tuned early, not discovered in the validation report.

Every production change is reversible. Mail routing, DNS, and cutover changes go through change

control with a documented rollback; keep source data intact through cutover so any wave can re-run.

Preserve the baseline. baseline-source.json is the source of truth for parity — capture it

before migrating and don't overwrite it.

## Safety & hygiene

Safe-by-default automation. The Python tools are read-only or --dry-run until --apply; keep

it that way. Review generated mapping/wave artifacts before importing them into the console.

Decommission cleanly. Only after the final wave validates: decommission the nodes and revoke

the migration app registration and service account so the powerful cross-tenant access does not   linger.

# Deliverables Summary

Everything included in this solution, on one page.

## Documentation

Solution Overview (01-solution-overview.md) — the Google Workspace Migrate architecture

(platform/worker nodes, database, connections, mappings, bridges), where it fits versus the other   migration solutions, the wave model, and the Assess → Design → Configure → Pilot → Validate →   Expand deployment model.

Requirements Guide (02-requirements.md) — solution-specific prerequisites (node platform,

M365 app registration + scopes, Google Cloud project + delegated service account, network egress,   source inventory, mapping/bridge data, service identities), each with how to verify/implement,   building on the shared Google global requirements.

Implementation Guide (03-implementation.md) — exact ordered steps: baseline, size the

platform, build connections and mappings, scan, run the pilot wave (pre-stage → delta → cutover),   validate, then expand — with pass/fail gates and documented rollback. Tool-console internals   deferred to Google's docs; procedure and sequencing given.

Testing & Validation (05-testing.md) — ten tests (T1–T10) mapped to the gates, each with an

explicit pass/fail result.

Troubleshooting (06-troubleshooting.md) — common failure modes (throttling/API limits,

connection/permission errors, delta/incomplete-item issues, mapping/bridge errors, mail-flow) and   resolutions.

Best Practices (07-best-practices.md) — durable practices for platform sizing, connections/

identity, waves/throttling/sequencing, validation, and change control.

Executive Summary (executive-summary.md) — outcome, approach, and why it is low-risk.

## Python tools (5) — Google Workspace Admin SDK / Microsoft Graph, safe-by-default

node-sizing-assessment.py — read-only source discovery (Microsoft Graph): inventories

mailbox/OneDrive/SharePoint counts, sizes, largest objects, and sharing complexity, and    recommends a worker-node count for a target throughput and window. Produces baseline-source.json,    the validation reference.

connection-mapping-generator.py — generates and validates the mapping CSVs and the

identity bridge (Bridge – Identity – Corp) Google Workspace Migrate consumes, from directory    data (Admin SDK + Graph). Dry-run/validate by default; never writes to a live system.

wave-batch-builder.py — groups in-scope users/sites into waves

(Migration Wave – <Scope> – <Stage>) and emits a throttling plan (concurrency, rate    ceilings) sized to stay under source/target API limits; --calibrate retunes from measured pilot    throughput.

migration-health-check.py — checks connection health and watches a running wave for

throughput, error rate, and sustained throttling (Graph 429 / Google rate limits), signaling    when to back off. Read-only.

post-migration-validation.py — post-wave validation report: target-vs-baseline

item-count parity, permission/ownership fidelity, and mail count + flow checks (Admin SDK / Drive    / Gmail read APIs). Read-only.

All scripts require Python 3.10+, use OAuth / ADC (no hardcoded credentials, no keys committed), take --help, and gate any write behind --apply (default is read-only or --dry-run).

## Packaged outputs

GWMIGRATE-Solution.pdf — the compiled solution document (all sections above).

GWMIGRATE-Scripts.zip — the five Python tools.

# Appendix A — PowerShell Scripts

The following scripts are included in the accompanying ZIP. Each script's own header documents its full usage and expected results.

## connection-mapping-generator.py

## migration-health-check.py

## node-sizing-assessment.py

## post-migration-validation.py

## wave-batch-builder.py