MDM Migration Readiness Assessment & Wave Planning

Implementation Solution Guide

Version 1.0.0    ·    2026-06-29

# Contents

Right-click and choose “Update Field” to build the table of contents.

# Executive Summary — MDM Migration Readiness Assessment & Wave Planning

Migrations · Vendor-neutral pre-migration assessment

Most MDM migrations fail in planning, not execution. Nobody has a clean inventory, the waves aren't thought through, and the risks surface mid-cutover during a change window with users watching. This solution is the planning discipline that runs before you touch a single device: a vendor-neutral MDM migration readiness assessment and wave plan — inventory the current estate, score readiness and risk, map dependencies, and produce a sequenced wave plan with explicit entry and exit criteria, validated against a pilot wave before it scales.

It is source-agnostic: it reads generic CSV exports from any MDM (Workspace ONE, MobileIron/Ivanti, Jamf, ManageEngine, SOTI, Configuration Manager, Intune, and others) and adds optional Microsoft Graph discovery when the current or target platform is Intune-adjacent. It plans the migration; it does not perform the cutover.

## What you get

A plain-language Solution Overview of the readiness-assessment model, what to inventory, and how

the wave plan is built.

A Requirements Guide with verify / implement-if-missing for every prerequisite.

An Implementation Guide of precise, ordered steps — inventory, validate completeness, fill gaps,

score readiness/risk, map dependencies, design waves, build cohorts, pilot, validate, expand.

Five PowerShell scripts for estate-inventory discovery, completeness validation, a

readiness/risk and wave-plan report, safe inventory-gap remediation, and a wave/cohort group builder.

Testing and Troubleshooting guides with explicit pass/fail gates.

## What this delivers

A complete, named set of planning artifacts — an Estate Inventory, a Readiness Scorecard, a Risk Register, a Dependency Map, a sequenced Wave Plan with Wave Cohorts, and per-wave Entry/Exit Criteria — so the actual migration runs to a script: lowest-risk, highest-readiness devices first, complex and critical devices last, and the plan proven on a pilot wave before any broad expansion.

## The deployment model

Assess → Configure → Pilot → Validate → Expand — with a mandatory gate to validate the plan against a pilot wave before it scales.

## Outcome

A clear-eyed picture of exactly what you are migrating and in what order — inventoried, scored, and sequenced — so the migration runs to a script instead of by surprise.

# 1. Solution Overview — MDM Migration Readiness Assessment & Wave Planning

## What this solution is

This is a vendor-neutral, pre-migration assessment and wave plan for moving a managed device estate from one Mobile Device Management (MDM) platform to another — for example Workspace ONE, MobileIron/Ivanti, Jamf, Kandji, ManageEngine, SOTI, Configuration Manager, or Group Policy moving to Microsoft Intune. It is the *planning* discipline that runs before a single device is touched: inventory the estate, score readiness and risk, find dependencies and blockers, then design a sequenced set of migration waves with explicit entry and exit criteria.

It does not perform the cutover. It produces the plan the cutover runs to.

## Why this matters (the why lives here, only here)

Most MDM migrations fail in planning, not execution. The recurring pattern is the same every time:

No clean inventory. Nobody can say exactly how many devices, which OS/platform mix, which apps,

which configuration profiles, which enrollment types, or which dependencies are in scope.

Waves aren't thought through. Devices are moved in an ad-hoc order, so high-risk or

high-dependency devices migrate before anyone has validated the approach on safe ones.

Risks surface mid-cutover. A blocker that should have been a line in a risk register on day one

instead becomes an outage during a change window with users watching.

The repeatable way fixes this by front-loading the discovery and the decision-making. When the estate is inventoried, readiness and risk are scored, and the waves are sequenced with entry/exit gates, the actual migration runs to a script instead of by surprise — and it is validated against a pilot wave before it scales.

## How it works

Inventory the estate. Collect every in-scope device with its OS/platform, ownership and

enrollment type, installed/required apps, assigned configuration profiles, compliance state, and    the user/department/region it belongs to — from the current MDM and from generic CSV inputs for any    source platform. The artifact is the Estate Inventory – MDM Migration – Assess.

Score readiness. Each device is scored against objective readiness criteria (supported OS,

reachable, enrolled, app coverage understood, no unsupported profile). The artifact is the    Readiness Scorecard – MDM Migration – Assess.

Score risk. Each device/app/profile is scored for migration risk (executive or

shared/critical device, kiosk/single-purpose, certificate or VPN dependency, unsupported    configuration). The artifact is the Risk Register – MDM Migration – Assess.

Map dependencies and blockers. Identify what must move together or in a fixed order —

certificates, Wi-Fi/VPN profiles, line-of-business apps, conditional-access bindings, shared-device    relationships. The artifact is the Dependency Map – MDM Migration – Assess.

Design the waves. Sequence devices into ordered waves from lowest risk/highest readiness to

highest risk/lowest readiness, each with entry and exit criteria. The artifacts are the    Wave Plan – MDM Migration – Configure and the Wave Cohorts – MDM Migration – Configure.

Validate against a pilot. The first wave is the Pilot Wave – MDM Migration – Pilot; it proves

the plan and the entry/exit gates before any broad expansion.

## What you inventory and score

Devices — count, hardware, ownership (corporate/BYOD), last check-in.

OS / platform mix — Windows / iOS / iPadOS / macOS / Android and version spread.

Apps — installed and required apps per device, including line-of-business and store apps.

Configuration profiles — Wi-Fi, VPN, email, certificates, restrictions, kiosk/single-purpose.

Compliance — current compliant/non-compliant state and the policy that sets it.

Enrollment types — corporate ADE/automatic, user-driven, BYOD, shared/kiosk.

Dependencies — certificate authorities, VPN, app dependencies, conditional access, shared-device.

## The named artifacts (use these exact names everywhere)

| Artifact | Stage |
| --- | --- |
| Estate Inventory – MDM Migration – Assess | Assess |
| Readiness Scorecard – MDM Migration – Assess | Assess |
| Risk Register – MDM Migration – Assess | Assess |
| Dependency Map – MDM Migration – Assess | Assess |
| Wave Plan – MDM Migration – Configure | Configure |
| Wave Cohorts – MDM Migration – Configure | Configure |
| Cohort Group – Per Wave – Configure | Configure |
| Pilot Wave – MDM Migration – Pilot | Pilot |
| Entry/Exit Criteria – Per Wave – Pilot | Pilot |

## What this is not

It is not the cutover itself — no devices are re-enrolled or unenrolled by this solution.

It is not vendor-specific tooling — it stays neutral about the source MDM and reads generic

CSV/inventory exports so it works regardless of where you are migrating from.

It does not assume the target is Intune, though the optional Microsoft Graph helpers light up

when the current or target MDM is Intune-adjacent.

## The standard deployment model

Assess → Configure → Pilot → Validate → Expand. Inventory and score (Assess), build the wave plan and cohorts (Configure), run the first wave (Pilot), prove the entry/exit gates and the plan against that pilot (Validate), then sequence the remaining waves (Expand). The plan is always validated against a pilot wave before it scales — that gate is non-negotiable.

# 2. Requirements Guide — MDM Migration Readiness Assessment & Wave Planning

Verify every requirement before assessing. Each entry: Description · Why · Verify · Implement-if-missing. Category-wide prerequisites (target tenant, target licensing, source access, inventory, enrollment, pilot/wave structure, change control) are in global-requirements-migrations.md and are assumed; the items below are specific to running this assessment and wave-planning work.

## 2.1 Read access to the current (source) MDM

Description: Administrative read access to the MDM you are migrating *from* (Workspace ONE, MobileIron/Ivanti, Jamf, ManageEngine, SOTI, Configuration Manager, Intune, etc.). Why: The estate is inventoried from the source console; without read access you cannot enumerate devices, apps, profiles, compliance, or enrollment types. Verify: You can sign in to the source console and open the device, app, and profile lists. Implement-if-missing: Request a read-only admin role / API credential from the source platform owner; this assessment never requires write access to the source.

## 2.2 An inventory export method (per source MDM)

Description: A way to export the source estate to CSV — a console export, a reporting view, or an API pull — covering devices, OS/platform, apps, profiles, compliance, enrollment type, and owner. Why: The assessment scripts read generic CSV/inventory inputs so they stay vendor-neutral; you need a repeatable export to feed them. Verify: You can produce a CSV of in-scope devices with at least device name, OS/platform, owner, and enrollment type columns. Implement-if-missing: Use the source console's export/report feature, or its API, to produce the CSV. Map its columns to the input schema documented in the Implementation Guide.

## 2.3 (Optional) Microsoft Graph access — when the current or target MDM is Intune-adjacent

Description: Microsoft Graph PowerShell SDK and read scopes (DeviceManagementManagedDevices.Read.All, DeviceManagementConfiguration.Read.All, DeviceManagementApps.Read.All) where Intune is the source *or* the target. Why: When Intune is in the picture, the discovery script can pull a live, structured inventory directly instead of relying only on CSV exports. Verify: Connect-MgGraph succeeds with the read scopes; Get-MgDeviceManagementManagedDevice returns devices. Implement-if-missing: Install-Module Microsoft.Graph -Scope CurrentUser; consent to the read scopes. This is optional — the assessment runs CSV-only for any non-Intune source.

## 2.4 Target-platform context (what you are migrating to)

Description: A documented statement of the target platform, its supported OS baselines, and its enrollment channels for each in-scope platform. Why: Readiness is scored relative to the target — a device on an OS the target no longer supports is a readiness gap, not just an inventory line. Verify: You can name the target platform and its minimum supported OS per platform in scope. Implement-if-missing: Capture the target's supported-OS matrix and enrollment prerequisites (see global-requirements-migrations.md G2 and G5) before scoring readiness.

## 2.5 A workstation to run the assessment scripts

Description: A Windows workstation with PowerShell 5.1 or PowerShell 7, able to reach the source export and (optionally) Microsoft Graph, with write access to an output folder for the artifacts. Why: The five PowerShell scripts generate the inventory, validation, report, and cohort artifacts to disk. Verify: \$PSVersionTable.PSVersion shows 5.1+ or 7+; you can write to the chosen output folder. Implement-if-missing: Use any managed admin workstation; create an output folder (e.g. C:\MDMRDY) and run the scripts from the scripts folder of this package.

## 2.6 Stakeholder input (owners, criticality, change windows)

Description: Business input on which users/departments/devices are executive, shared, kiosk, or mission-critical, and any blackout/change-window constraints. Why: Risk scoring and wave sequencing depend on business criticality and change windows that no inventory export contains. Verify: You have a named contact per department/region who can confirm criticality and windows. Implement-if-missing: Run a short stakeholder intake; record criticality and constraints as input columns so they feed the Risk Register – MDM Migration – Assess and the Wave Plan – MDM Migration – Configure.

## 2.7 Defined scope boundary

Description: A written statement of what is in and out of scope (sites, platforms, ownership types, retired devices). Why: An unbounded inventory inflates risk and waves with devices that should be excluded or decommissioned, not migrated. Verify: The scope statement names included platforms/sites and explicitly excludes retired or out-of-scope devices. Implement-if-missing: Agree the scope boundary with the migration sponsor before inventory; encode exclusions as a filter on the CSV input.

__________________________________________________

## Checklist

Read access to the current (source) MDM

An inventory export method that produces CSV (devices, OS, apps, profiles, compliance, enrollment, owner)

(Optional) Microsoft Graph read access when Intune is source or target

Target-platform context (supported OS baselines + enrollment channels)

A workstation with PowerShell 5.1/7 and an output folder

Stakeholder input on criticality and change windows

A written scope boundary (in/out of scope)

Category global requirements confirmed (global-requirements-migrations.md)

# 3. Implementation Guide — MDM Migration Readiness Assessment & Wave Planning

Follow these steps in order. This is a planning engagement: the output is a set of named artifacts, not a changed device. The model is Assess → Configure → Pilot → Validate → Expand, with a hard gate that the plan is validated against a pilot wave before it scales.

Vendor-neutral note: every step reads either a generic CSV export from the source MDM or, when the current/target MDM is Intune-adjacent, a live Microsoft Graph pull. No step requires write access to the source platform.

## The input schema (map your source export to these columns)

The scripts read a CSV (the raw estate export) with these columns. Map your source MDM's export columns to these names, or let MDMRDY-Discovery.ps1 build them from Microsoft Graph.

| Column | Meaning |
| --- | --- |
| DeviceName | Unique device identifier/name |
| Platform | Windows / iOS / iPadOS / macOS / Android |
| OSVersion | Current OS version string |
| Owner | User principal name or owner identifier |
| Department | Department/business unit |
| Region | Site/region |
| EnrollmentType | Corporate-ADE / UserDriven / BYOD / Shared / Kiosk |
| Compliance | Compliant / NonCompliant / Unknown |
| LastCheckIn | Last check-in date (ISO 8601) |
| Apps | Semicolon-separated app list (or app count) |
| Profiles | Semicolon-separated profile list (Wi-Fi;VPN;Cert;Email;Restrictions;Kiosk) |
| Criticality | Standard / Executive / Critical (from stakeholder input) |

## Stage 1 — Assess (inventory + score)

### Step 1 — Inventory the estate

Produce the raw export from the source MDM (CSV), or confirm Microsoft Graph read access if Intune

is source/target.

From the scripts folder run the discovery (read-only):

CSV source: powershell -ExecutionPolicy Bypass -File .\MDMRDY-Discovery.ps1 -InputCsv .\source-export.csv -OutputFolder C:\MDMRDY

Intune source: powershell -ExecutionPolicy Bypass -File .\MDMRDY-Discovery.ps1 -UseGraph -OutputFolder C:\MDMRDY

Output: the Estate Inventory – MDM Migration – Assess (a normalized CSV of every in-scope device

with platform, OS, owner, department/region, enrollment type, compliance, apps, and profiles).

### Step 2 — Validate inventory completeness

Run the validation (read-only) against the inventory:

powershell -ExecutionPolicy Bypass -File .\MDMRDY-Validation.ps1 -InventoryCsv C:\MDMRDY\estate-inventory.csv -OutputFolder C:\MDMRDY

It flags missing/blank fields, unknown platforms, stale check-ins, and rows that cannot be scored.

Output: a data-completeness report. Do not score readiness until completeness passes the gate in

the Testing Guide (Test 1).

### Step 3 — Fill inventory gaps (safe remediation)

Where rows are incomplete, run the remediation in its default `-WhatIf` mode first to preview

the fills:    powershell -ExecutionPolicy Bypass -File .\MDMRDY-Remediation.ps1 -InventoryCsv C:\MDMRDY\estate-inventory.csv -OutputFolder C:\MDMRDY

Review the proposed fills (defaulting unknown enrollment type, inferring platform from OS, marking

stale devices for review). Re-run with -Apply only when the proposed changes are correct.

Output: a completed Estate Inventory – MDM Migration – Assess ready to score.

### Step 4 — Score readiness and risk, map dependencies

Run the report (read-only) over the completed inventory:

powershell -ExecutionPolicy Bypass -File .\MDMRDY-Report.ps1 -InventoryCsv C:\MDMRDY\estate-inventory.csv -OutputFolder C:\MDMRDY

It produces, in one pass:

the Readiness Scorecard – MDM Migration – Assess (per-device readiness score 0–100 against

supported OS, reachable/recent check-in, enrolled, app coverage understood, no unsupported      profile),

the Risk Register – MDM Migration – Assess (per-device risk score and the contributing risk

factors: executive/critical, shared/kiosk, certificate/VPN dependency, unsupported config,      non-compliant, stale),

the Dependency Map – MDM Migration – Assess (what must move together/in order: certificates,

Wi-Fi/VPN, line-of-business apps, conditional access, shared-device groupings),

and a draft Wave Plan – MDM Migration – Configure with suggested wave assignment.

## Stage 2 — Configure (design the waves)

### Step 5 — Finalize the wave plan and cohorts

Review the draft wave plan with stakeholders; adjust assignments for criticality and change

windows that only the business knows.

The wave model sequences from lowest risk / highest readiness to **highest risk / lowest

readiness**:

Wave 0 — Pilot: a small, low-risk, high-readiness, representative cross-section.

Wave 1 — Early: standard devices, no special dependencies.

Wave 2 — Broad: the bulk of standard devices.

Wave 3 — Complex/Critical: executive, shared/kiosk, certificate/VPN-dependent, low-readiness.

Each wave carries an Entry/Exit Criteria – Per Wave – Pilot block (see Step 6).

Output: the finalized Wave Plan – MDM Migration – Configure and the

Wave Cohorts – MDM Migration – Configure (the per-wave device membership lists).

### Step 6 — Define entry/exit criteria per wave

Record, for every wave, the Entry/Exit Criteria – Per Wave – Pilot:

Entry: prior wave exited cleanly; target enrollment channel active for the platforms in this

wave (global-requirements-migrations.md G5); rollback path documented (G7); cohort group built.

Exit: all devices in the cohort migrated and enrolled in the target; compliance re-established;

no open severity-1 issue; user-impact tickets below the agreed threshold.

### Step 7 — Build the cohort groups

Materialize each wave's membership as a Cohort Group – Per Wave – Configure.

Build the groups from the cohort lists:

Export-only (any MDM): powershell -ExecutionPolicy Bypass -File .\MDMRDY-Set-WaveCohortTargeting.ps1 -CohortsCsv C:\MDMRDY\wave-cohorts.csv -OutputFolder C:\MDMRDY — writes per-wave membership CSVs you can import into the target's grouping system.

Entra/Intune target: add -CreateEntraGroups -WhatIf to preview, then -CreateEntraGroups -Apply to create one Microsoft Entra security group per wave and add members (requires Graph Group.ReadWrite.All).

Naming: each group is Cohort Group – Per Wave – Configure, suffixed with the wave label (e.g.

MDMRDY-Wave0-Pilot, MDMRDY-Wave1-Early).

## Stage 3 — Pilot

### Step 8 — Run the pilot wave

The Pilot Wave – MDM Migration – Pilot (Wave 0) is the first cohort to migrate, using your

separate migration runbook (this solution plans; it does not cut over).

Confirm the pilot meets its Entry/Exit Criteria – Per Wave – Pilot before starting.

## Stage 4 — Validate (the gate)

### Step 9 — Validate the plan against the pilot

After the pilot wave migrates, re-run MDMRDY-Discovery.ps1 and MDMRDY-Report.ps1 against the

post-pilot estate to confirm the pilot's exit criteria are met and the readiness/risk model held.

Reconcile predicted vs. actual: did the readiness scores predict the smooth devices, and did the

risk register predict the friction? Adjust the scoring weights and the remaining waves if not.

Do not expand until the pilot wave passes its exit criteria and the plan is validated. This is

the mandatory gate.

## Stage 5 — Expand

### Step 10 — Sequence the remaining waves

With the plan validated, release the remaining waves in order, each gated by its

Entry/Exit Criteria – Per Wave – Pilot.

Re-run MDMRDY-Report.ps1 after each wave to keep the readiness/risk picture and the cohorts

current as devices leave the source estate.

__________________________________________________

### Order of operations

Inventory (Discovery) → Validate completeness → Fill gaps (Remediation, -WhatIf first) → Score readiness/risk + dependencies (Report) → Finalize Wave Plan + Cohorts → Entry/Exit criteria → Build cohort groups → Pilot wave → Validate plan against pilot (gate) → Expand remaining waves

# 5. Testing Guide — MDM Migration Readiness Assessment & Wave Planning

Run these tests as you produce each artifact. The whole point is that the plan is validated against a pilot wave before it scales (Tests 6–7), so no artifact is "done" until its gate passes.

## Test 1 — Inventory completeness

Do: Run MDMRDY-Validation.ps1 against the Estate Inventory – MDM Migration – Assess. Expected: No blank required fields (DeviceName, Platform, OSVersion, EnrollmentType, Owner); no unknown platforms; stale check-ins flagged for review. Completeness at or above the agreed threshold.

## Test 2 — Inventory matches the source

Do: Compare the inventory device count and platform mix against the source MDM console totals. Expected: Counts reconcile within the agreed tolerance; any difference is explained by the scope boundary (excluded/retired devices).

## Test 3 — Readiness scorecard is populated and sane

Do: Open the Readiness Scorecard – MDM Migration – Assess. Expected: Every in-scope device has a readiness score 0–100; devices on unsupported OS or with unknown app/profile coverage score low; recent, supported, enrolled devices score high.

## Test 4 — Risk register flags the real risks

Do: Open the Risk Register – MDM Migration – Assess. Expected: Executive/critical, shared/kiosk, certificate/VPN-dependent, non-compliant, and stale devices carry elevated risk with the contributing factors named; standard devices score low.

## Test 5 — Dependencies and waves are coherent

Do: Cross-check the Dependency Map – MDM Migration – Assess against the Wave Plan – MDM Migration – Configure and Wave Cohorts – MDM Migration – Configure. Expected: Devices that must move together share a wave; high-risk/low-readiness devices land in later waves; the Pilot Wave – MDM Migration – Pilot is low-risk, high-readiness, and representative; every device appears in exactly one wave.

## Test 6 — Cohort groups built correctly

Do: Run MDMRDY-Set-WaveCohortTargeting.ps1; inspect the per-wave membership output (and, if created, the Entra security groups). Expected: Each Cohort Group – Per Wave – Configure contains exactly its cohort's devices; no device is in two groups; group names match the wave labels.

## Test 7 — Plan validated against the pilot wave (the gate)

Do: After the pilot migrates, re-run MDMRDY-Discovery.ps1 and MDMRDY-Report.ps1 over the post-pilot estate and check the pilot's Entry/Exit Criteria – Per Wave – Pilot. Expected: Pilot devices migrated, enrolled in the target, and compliant; predicted readiness/risk matched the actual outcome; no open severity-1 issue. Scoring weights tuned if prediction missed.

__________________________________________________

## Pass/fail gate

| Gate | Requirement |
| --- | --- |
| Assess pass | Tests 1–4 pass; inventory reconciles to source; readiness and risk scored for every in-scope device |
| Configure pass | Test 5–6 pass; every device in exactly one wave; pilot wave is low-risk/high-readiness/representative; entry/exit criteria written per wave |
| Pilot/Validate pass | Test 7 passes; pilot wave meets its exit criteria and the readiness/risk model is confirmed before any expansion |

# 6. Troubleshooting Guide — MDM Migration Readiness Assessment & Wave Planning

Use MDMRDY-Validation.ps1 for inventory data quality, MDMRDY-Report.ps1 to re-score, and MDMRDY-Remediation.ps1 (default -WhatIf) to safely fill gaps. All discovery/validation/report steps are read-only.

## A. Inventory problems

| Symptom | Cause | Remediation |
| --- | --- | --- |
| Inventory count doesn't match the source console | Scope filter too wide/narrow, or stale/retired devices included | Reconcile against the scope boundary; exclude retired devices; re-run MDMRDY-Discovery.ps1 |
| Blank required fields (Platform, EnrollmentType, Owner) | Source export omitted columns or used different headers | Map source columns to the input schema (Implementation Guide); run MDMRDY-Remediation.ps1 -WhatIf then -Apply to fill defaults |
| Unknown platform values | Source uses non-standard platform labels | Normalize to Windows/iOS/iPadOS/macOS/Android; remediation infers platform from OSVersion where possible |
| Devices with very old LastCheckIn | Decommissioned or lost devices still in source | Flag stale in validation; exclude from waves or route to a decommission list, not a migration wave |

## B. Microsoft Graph (optional, Intune-adjacent) issues

| Symptom | Cause | Remediation |
| --- | --- | --- |
| Connect-MgGraph fails | SDK missing or scopes not consented | Install-Module Microsoft.Graph -Scope CurrentUser; consent to the read scopes in Requirements 2.3 |
| Graph returns no devices | Wrong tenant or insufficient role | Confirm you signed into the correct tenant with a role that can read managed devices |
| You don't use Intune at all | Source is a non-Intune MDM | Skip -UseGraph; run CSV-only — the assessment is fully vendor-neutral without Graph |

## C. Scoring looks wrong

| Symptom | Cause | Remediation |
| --- | --- | --- |
| Everything scores low-readiness | Target supported-OS baseline not provided | Supply the target's supported-OS matrix; re-run MDMRDY-Report.ps1 |
| Critical devices score low-risk | Stakeholder criticality not fed in | Populate the Criticality column from stakeholder input; re-run the report |
| Readiness and actual pilot outcome disagree | Scoring weights mis-tuned | Reconcile predicted vs. actual after the pilot; adjust weights and re-score the remaining waves |

## D. Wave / cohort problems

| Symptom | Cause | Remediation |
| --- | --- | --- |
| A device appears in two waves | Overlapping cohort filters | Re-run MDMRDY-Set-WaveCohortTargeting.ps1; ensure each device maps to exactly one wave |
| Dependent devices split across waves | Dependency map not applied to sequencing | Use the Dependency Map – MDM Migration – Assess to co-locate dependent devices in one wave |
| Entra group creation denied | Missing Group.ReadWrite.All | Grant the write scope, or use export-only mode and import the membership CSVs into the target manually |

## E. Pilot validation gate

If the Pilot Wave – MDM Migration – Pilot does not meet its Entry/Exit Criteria – Per Wave – Pilot,

do not expand. Resolve the failing criterion, re-run discovery + report over the post-pilot   estate, and only proceed once the exit criteria pass and the model is confirmed.

## F. Diagnostics quick reference

# Re-check inventory completeness
.\MDMRDY-Validation.ps1 -InventoryCsv C:\MDMRDY\estate-inventory.csv -OutputFolder C:\MDMRDY
# Preview gap fills without changing the source of truth
.\MDMRDY-Remediation.ps1 -InventoryCsv C:\MDMRDY\estate-inventory.csv -OutputFolder C:\MDMRDY   # -WhatIf is the default
# Re-score after fixing inputs
.\MDMRDY-Report.ps1 -InventoryCsv C:\MDMRDY\estate-inventory.csv -OutputFolder C:\MDMRDY

## G. When to escalate

If the inventory reconciles to the source, completeness passes, the target baseline and criticality are supplied, and the readiness/risk scores still do not match what the pilot wave actually experienced, pause the expansion and review the scoring model and the dependency map with the migration sponsor before sequencing further waves.

# 7. Best Practices — MDM Migration Readiness Assessment & Wave Planning

Inventory before you opinion. Build the Estate Inventory – MDM Migration – Assess first and

reconcile it to the source console totals. Every later decision (readiness, risk, waves) is only as   good as this inventory — a migration planned on a guess fails on a guess.

Score against the target, not in a vacuum. Readiness is relative: a device on an OS the *target*

no longer supports is a readiness gap. Capture the target's supported-OS matrix before scoring the   Readiness Scorecard – MDM Migration – Assess.

Make business criticality an input, not an afterthought. No inventory export knows which devices

are executive, shared, or mission-critical. Feed stakeholder criticality into the   Risk Register – MDM Migration – Assess so the risky devices land in later waves.

Sequence low-risk/high-readiness first. Always migrate the safest, most-ready devices early so

the approach is proven before complex or critical devices move. The   Pilot Wave – MDM Migration – Pilot must be low-risk, high-readiness, and representative.

Respect dependencies — move what must move together. Use the

Dependency Map – MDM Migration – Assess to keep certificate/VPN/app/conditional-access and   shared-device groupings in the same wave; a split dependency is an outage waiting for a change   window.

Write entry and exit criteria for every wave. A wave without an

Entry/Exit Criteria – Per Wave – Pilot block has no gate, so it never truly "finishes" and risk   piles into the next wave. Define both before the wave starts.

Validate the plan against the pilot before you scale. Re-run the report over the post-pilot

estate and reconcile predicted vs. actual; tune the scoring weights if the pilot surprised you. Do   not expand on an unvalidated plan — this is the one gate you never skip.

Keep it vendor-neutral and repeatable. Drive everything from the CSV input schema (or Graph

when Intune-adjacent) so the same assessment runs against any source MDM and the next migration   reuses the artifacts and names verbatim.

Re-run discovery as the estate drains. After each wave, re-run MDMRDY-Discovery.ps1 and

MDMRDY-Report.ps1 so the inventory, scores, and cohorts stay current as devices leave the source.

Preview before you change anything. Run MDMRDY-Remediation.ps1 in its default -WhatIf mode

and review the proposed inventory fills before -Apply; never let an automated fill silently rewrite   the source of truth.

Name everything once and reuse it. Use the exact artifact names

(<Purpose> – <Scope> – <Stage>) across the inventory, scorecard, risk register, dependency map,   wave plan, cohorts, and groups so the plan reads the same in every document and tool.

# 8. Deliverables Summary — MDM Migration Readiness Assessment & Wave Planning

## Documentation

| Document | Purpose |
| --- | --- |
| Executive Summary | Business case and what's in the box |
| 1. Solution Overview | What the assessment is, what to inventory, readiness/risk scoring, wave model, and the why |
| 2. Requirements Guide | Every prerequisite with Verify / Implement-if-missing |
| Global Requirements (Migrations) | Category-wide prerequisites, published once |
| 3. Implementation Guide | Exact, ordered steps: inventory, validate, fill gaps, score, design waves, build cohorts, pilot, validate, expand |
| 5. Testing Guide | Validation procedures with pass/fail gates |
| 6. Troubleshooting Guide | Field issues and remediation |
| 7. Best Practices | Field-proven recommendations |

## PowerShell scripts

| Script | What it does |
| --- | --- |
| MDMRDY-Discovery.ps1 | Builds the Estate Inventory – MDM Migration – Assess from a source CSV export or (optional) Microsoft Graph. Read-only. |
| MDMRDY-Validation.ps1 | Checks inventory data completeness (missing fields, unknown platforms, stale check-ins). Read-only. |
| MDMRDY-Report.ps1 | Produces the Readiness Scorecard, Risk Register, Dependency Map, and a draft Wave Plan in one pass. Read-only. |
| MDMRDY-Remediation.ps1 | Safely fills inventory gaps; default -WhatIf, applies only with -Apply. |
| MDMRDY-Set-WaveCohortTargeting.ps1 | Builds the Wave Cohorts / Cohort Group – Per Wave – Configure membership (export CSV, or optional Entra security groups). |

## Named artifacts produced

| Artifact | Stage |
| --- | --- |
| Estate Inventory – MDM Migration – Assess | Assess |
| Readiness Scorecard – MDM Migration – Assess | Assess |
| Risk Register – MDM Migration – Assess | Assess |
| Dependency Map – MDM Migration – Assess | Assess |
| Wave Plan – MDM Migration – Configure | Configure |
| Wave Cohorts – MDM Migration – Configure | Configure |
| Cohort Group – Per Wave – Configure | Configure |
| Pilot Wave – MDM Migration – Pilot | Pilot |
| Entry/Exit Criteria – Per Wave – Pilot | Pilot |

## What the buyer receives

This assessment and wave-planning guide as a branded Word document and PDF.

All five PowerShell scripts in a single ZIP.

A repeatable, vendor-neutral process following the model: Assess → Configure → Pilot → Validate → Expand.

## Outcome

A clear-eyed picture of exactly what is being migrated and in what order — the estate inventoried, readiness and risk scored, dependencies mapped, and a sequenced wave plan with entry/exit criteria — validated against a pilot wave before it scales, so the migration runs to a script instead of by surprise.

# Appendix A — PowerShell Scripts

The following scripts are included in the accompanying ZIP. Each script's own header documents its full usage and expected results.

## MDMRDY-Discovery.ps1

Purpose: Produces the "Estate Inventory - MDM Migration - Assess" artifact: a normalized CSV of every in-scope device with platform, OS, owner, department/region, enrollment type, compliance, apps, and profiles. Reads a generic CSV export from ANY source MDM, or (optional) pulls a live inventory from Microsoft Graph when the current/target MDM is Intune-adjacent. Read-only: it never writes to the source platform. HOW TO RUN CSV source (any MDM): powershell -ExecutionPolicy Bypass -File .\MDMRDY-Discovery.ps1 -InputCsv .\source-export.csv -OutputFolder C:\MDMRDY Intune source/target (optional): powershell -ExecutionPolicy Bypass -File .\MDMRDY-Discovery.ps1 -UseGraph -OutputFolder C:\MDMRDY Graph mode needs Microsoft.Graph SDK and DeviceManagementManagedDevices.Read.All. EXPECTED RESULTS Writes estate-inventory.csv (the "Estate Inventory - MDM Migration - Assess") to the output folder and prints a device/platform summary. No source-side changes. .NOTES Migrations — vendor-neutral pre-migration assessment. Read-only. #> [CmdletBinding()] param( [string]$InputCsv, [switch]$UseGraph, [string]$OutputFolder = (Join-Path $PWD 'MDMRDY') )

How to run: CSV source (any MDM): powershell -ExecutionPolicy Bypass -File .\MDMRDY-Discovery.ps1 -InputCsv .\source-export.csv -OutputFolder C:\MDMRDY Intune source/target (optional): powershell -ExecutionPolicy Bypass -File .\MDMRDY-Discovery.ps1 -UseGraph -OutputFolder C:\MDMRDY Graph mode needs Microsoft.Graph SDK and DeviceManagementManagedDevices.Read.All. EXPECTED RESULTS Writes estate-inventory.csv (the "Estate Inventory - MDM Migration - Assess") to the output folder and prints a device/platform summary. No source-side changes. .NOTES Migrations — vendor-neutral pre-migration assessment. Read-only. #> [CmdletBinding()] param( [string]$InputCsv, [switch]$UseGraph, [string]$OutputFolder = (Join-Path $PWD 'MDMRDY') )

## MDMRDY-Remediation.ps1

Purpose: Fills gaps in the "Estate Inventory - MDM Migration - Assess" so it can be scored: defaults an unknown EnrollmentType to 'UserDriven', infers Platform from OSVersion where blank, and marks stale or unscoreable rows for review. SAFE BY DEFAULT: previews changes with -WhatIf and writes nothing until you pass -Apply. It never touches the source MDM — only the local inventory CSV. HOW TO RUN Preview (default): powershell -ExecutionPolicy Bypass -File .\MDMRDY-Remediation.ps1 -InventoryCsv C:\MDMRDY\estate-inventory.csv -OutputFolder C:\MDMRDY Apply (writes a remediated copy): powershell -ExecutionPolicy Bypass -File .\MDMRDY-Remediation.ps1 -InventoryCsv C:\MDMRDY\estate-inventory.csv -OutputFolder C:\MDMRDY -Apply EXPECTED RESULTS -WhatIf: prints each proposed fill, writes nothing. -Apply : writes estate-inventory-remediated.csv with the fills applied; original is untouched. .NOTES Migrations — vendor-neutral pre-migration assessment. Default -WhatIf; -Apply to change the copy. #> [CmdletBinding()] param( [Parameter(Mandatory)][string]$InventoryCsv, [string]$OutputFolder = (Join-Path $PWD 'MDMRDY'), [switch]$Apply )

How to run: Preview (default): powershell -ExecutionPolicy Bypass -File .\MDMRDY-Remediation.ps1 -InventoryCsv C:\MDMRDY\estate-inventory.csv -OutputFolder C:\MDMRDY Apply (writes a remediated copy): powershell -ExecutionPolicy Bypass -File .\MDMRDY-Remediation.ps1 -InventoryCsv C:\MDMRDY\estate-inventory.csv -OutputFolder C:\MDMRDY -Apply EXPECTED RESULTS -WhatIf: prints each proposed fill, writes nothing. -Apply : writes estate-inventory-remediated.csv with the fills applied; original is untouched. .NOTES Migrations — vendor-neutral pre-migration assessment. Default -WhatIf; -Apply to change the copy. #> [CmdletBinding()] param( [Parameter(Mandatory)][string]$InventoryCsv, [string]$OutputFolder = (Join-Path $PWD 'MDMRDY'), [switch]$Apply )

## MDMRDY-Report.ps1

Purpose: From the "Estate Inventory - MDM Migration - Assess", produces in one pass: - "Readiness Scorecard - MDM Migration - Assess"  (per-device readiness 0-100) - "Risk Register - MDM Migration - Assess"        (per-device risk + factors) - "Dependency Map - MDM Migration - Assess"       (what must move together) - draft "Wave Plan - MDM Migration - Configure"   (suggested wave per device) Read-only: it computes scores from the inventory and writes report CSVs only. HOW TO RUN powershell -ExecutionPolicy Bypass -File .\MDMRDY-Report.ps1 -InventoryCsv C:\MDMRDY\estate-inventory.csv -OutputFolder C:\MDMRDY Optional: -SupportedOS @{ Windows='10.0.19045'; iOS='16'; iPadOS='16'; macOS='13'; Android='12' } -StaleDays 90 EXPECTED RESULTS Writes readiness-scorecard.csv, risk-register.csv, dependency-map.csv, and wave-plan-draft.csv, then prints a readiness/risk and wave-distribution summary. .NOTES Migrations — vendor-neutral pre-migration assessment. Read-only. #> [CmdletBinding()] param( [Parameter(Mandatory)][string]$InventoryCsv, [string]$OutputFolder = (Join-Path $PWD 'MDMRDY'), [hashtable]$SupportedOS = @{ Windows='10.0.19044'; iOS='16'; iPadOS='16'; macOS='13'; Android='11' }, [int]$StaleDays = 90 )

How to run: powershell -ExecutionPolicy Bypass -File .\MDMRDY-Report.ps1 -InventoryCsv C:\MDMRDY\estate-inventory.csv -OutputFolder C:\MDMRDY Optional: -SupportedOS @{ Windows='10.0.19045'; iOS='16'; iPadOS='16'; macOS='13'; Android='12' } -StaleDays 90 EXPECTED RESULTS Writes readiness-scorecard.csv, risk-register.csv, dependency-map.csv, and wave-plan-draft.csv, then prints a readiness/risk and wave-distribution summary. .NOTES Migrations — vendor-neutral pre-migration assessment. Read-only. #> [CmdletBinding()] param( [Parameter(Mandatory)][string]$InventoryCsv, [string]$OutputFolder = (Join-Path $PWD 'MDMRDY'), [hashtable]$SupportedOS = @{ Windows='10.0.19044'; iOS='16'; iPadOS='16'; macOS='13'; Android='11' }, [int]$StaleDays = 90 )

## MDMRDY-Set-WaveCohortTargeting.ps1

Purpose: Materializes the "Wave Cohorts - MDM Migration - Configure" from the finalized wave plan: one membership list per wave ("Cohort Group - Per Wave - Configure"). By default it writes export CSVs you can import into ANY target's grouping system (vendor-neutral). When the target is Entra/Intune, -CreateEntraGroups creates one Microsoft Entra security group per wave and adds members. Group creation is gated: -WhatIf previews, -Apply commits. HOW TO RUN Export-only (any MDM): powershell -ExecutionPolicy Bypass -File .\MDMRDY-Set-WaveCohortTargeting.ps1 -CohortsCsv C:\MDMRDY\wave-plan-draft.csv -OutputFolder C:\MDMRDY Entra/Intune target — preview then apply: ... -CreateEntraGroups -WhatIf ... -CreateEntraGroups -Apply Entra mode needs Microsoft.Graph SDK and Group.ReadWrite.All. The cohorts CSV needs at least: DeviceName, SuggestedWave (or WaveLabel). EXPECTED RESULTS Writes one cohort-<WaveLabel>.csv per wave (the "Cohort Group - Per Wave - Configure"). With -CreateEntraGroups -Apply, also creates Entra security groups named MDMRDY-<WaveLabel> and adds device members. -WhatIf changes nothing in Entra. .NOTES Migrations — vendor-neutral pre-migration assessment. Export-only is read-only; Entra writes only with -Apply. #> [CmdletBinding()] param( [Parameter(Mandatory)][string]$CohortsCsv, [string]$OutputFolder = (Join-Path $PWD 'MDMRDY'), [switch]$CreateEntraGroups, [switch]$Apply )

How to run: Export-only (any MDM): powershell -ExecutionPolicy Bypass -File .\MDMRDY-Set-WaveCohortTargeting.ps1 -CohortsCsv C:\MDMRDY\wave-plan-draft.csv -OutputFolder C:\MDMRDY Entra/Intune target — preview then apply: ... -CreateEntraGroups -WhatIf ... -CreateEntraGroups -Apply Entra mode needs Microsoft.Graph SDK and Group.ReadWrite.All. The cohorts CSV needs at least: DeviceName, SuggestedWave (or WaveLabel). EXPECTED RESULTS Writes one cohort-<WaveLabel>.csv per wave (the "Cohort Group - Per Wave - Configure"). With -CreateEntraGroups -Apply, also creates Entra security groups named MDMRDY-<WaveLabel> and adds device members. -WhatIf changes nothing in Entra. .NOTES Migrations — vendor-neutral pre-migration assessment. Export-only is read-only; Entra writes only with -Apply. #> [CmdletBinding()] param( [Parameter(Mandatory)][string]$CohortsCsv, [string]$OutputFolder = (Join-Path $PWD 'MDMRDY'), [switch]$CreateEntraGroups, [switch]$Apply )

## MDMRDY-Validation.ps1

Purpose: Validates the "Estate Inventory - MDM Migration - Assess" for completeness: missing/blank required fields, unknown platform values, and stale check-ins. Gates the assessment so you do not score readiness/risk on bad data. Read-only — reports issues, changes nothing. HOW TO RUN powershell -ExecutionPolicy Bypass -File .\MDMRDY-Validation.ps1 -InventoryCsv C:\MDMRDY\estate-inventory.csv -OutputFolder C:\MDMRDY Optional: -StaleDays 90 (default) sets the stale check-in threshold. EXPECTED RESULTS Prints a completeness summary and writes validation-report.csv listing every flagged row and reason. A clean run (no blanks, known platforms) means the inventory is ready to score. .NOTES Migrations — vendor-neutral pre-migration assessment. Read-only. #> [CmdletBinding()] param( [Parameter(Mandatory)][string]$InventoryCsv, [string]$OutputFolder = (Join-Path $PWD 'MDMRDY'), [int]$StaleDays = 90 )

How to run: powershell -ExecutionPolicy Bypass -File .\MDMRDY-Validation.ps1 -InventoryCsv C:\MDMRDY\estate-inventory.csv -OutputFolder C:\MDMRDY Optional: -StaleDays 90 (default) sets the stale check-in threshold. EXPECTED RESULTS Prints a completeness summary and writes validation-report.csv listing every flagged row and reason. A clean run (no blanks, known platforms) means the inventory is ready to score. .NOTES Migrations — vendor-neutral pre-migration assessment. Read-only. #> [CmdletBinding()] param( [Parameter(Mandatory)][string]$InventoryCsv, [string]$OutputFolder = (Join-Path $PWD 'MDMRDY'), [int]$StaleDays = 90 )